Informative translation

CONTRACT OF COMMAND

concluded pursuant to § 2430 et seq. of Act No. 89/2012 Coll., the Civil Code, as amended, between the contracting parties:

Contracting Parties

- SAKO Brno, a.s.

with registered office: 	Jedovnická 4247/2, 628 00 Brno

represented by:      		Ing. Pavel Urubek, Chairman of the Board of Directors,

Ing. Daniel Struž, MBA, Vice-Chairman of the Board of Directors

ID:		60713470

TIN:                    		CZ60713470

Bank connection: 			Komerční banka, a.s. Brno - countryside

Account number: 		79033621/0100

Registered in the Commercial Register maintained by the Regional Court in Brno, file no. B 1371

persons authorized under Article XIV, paragraph 7 of the Contract:

a) Ing. Karel Jelínek, tel. 739 468 191, e-mail jelinek@sako.cz

b) Ing. Martin Mužila, tel. 603 140 618, e-mail muzila@sako.cz

c) Ing. Pavel Slezák, Ph.D., tel. 734 144 001, e-mail pavel.slezak@sako.cz

(hereinafter referred to as "Principal" or "Customer")

- Brněnské komunikace a.s.

Based	Renneská třída 787/1a, Štýřice, 639 00 Brno

Represented by	Ing. David Grund, Chairman of the Board of Directors

JUDr. Michal Marek, Vice-Chairman of the Board of Directors

ID	60733098

TIN	CZ60733098

Bank connection:	Československá obchodní banka, a.s.

Account number:	382286023/0300

Registered in the Commercial Register maintained by the Regional Court in Brno, file no. B 1479

persons authorized under Article XIV, paragraph 7 of the Contract:

a) Ing. Luděk Borový, tel. 602 133 447, e-mail borovy@bkom.cz

b) Ing. Jan Strmiska, tel. 603 748 887, e-mail strmiska@bkom.cz

(hereinafter referred to as "Agent" or "Construction Manager")

(Principal and Principal together as "Parties")

The Parties, being aware of their obligations contained in this Agreement and intending to be bound by this Agreement, agree and consent to the following wording of the Agreement:

PREAMBLE

Between the Principal and the Contractor a Contract for Work has been or will be concluded for the execution of the Work entitled "Modernization of the ZEVO of SAKO Brno". The Principal's objective is to ensure proper control, supervision and coordination of the preparation, execution, commissioning and approval of the Work.

I.

DEFINITIONS

- The Parties agree that the following terms used in this Agreement shall have the meanings specified below in this Article I of the Agreement:

  - SAKO premises means immovable property, including parts and accessories, owned by the Principal, intended for the implementation of the project "Modernization of the ZEVO of SAKO Brno", which will be used by the Contractor for the execution of the Work. As of the date of conclusion of this Contract, it consists of the immovable property specified in the Supporting Documentation; After the execution of the Construction, the Line will be part of the SAKO Site;

  - Price of the Work means the total price at which the Contractor shall perform the Work for the Principal, subject to the definition and adjustment of the Price of the Work in the Contract for the Work for the purposes of this Agreement;

  - The activity of the Construction Manager means that the Agent undertakes to perform complex construction management services for the Principal, on his behalf and on his account - i.e. project management and technical consultancy services in accordance with this Agreement, including checking the compliance of the preparation and implementation of the Work with the Construction Contract and the Legal Regulations, whereby in relation to binding guidelines, methodologies and other regulations, CSN standards and the conditions of the subsidy pursuant to paragraphs1.21 (b) (b) , (c) and (e) of this Agreement, such checking shall be carried out in the form of indeitifcation of apparent non-compliance with such Legal Regulations;

  - day means calendar day;

  - Additional Services means the sum of all activities of the Agent provided under this Agreement that are not included in the Construction Manager Activities, performed by the Agent at the direction of the Principal;

  - Work means the sum of all activities under the Work Contract that are necessary to deliver a Line that meets the requirements under the Work Contract and achieves the results contemplated by the Work Contract and are necessary for the operation of the Line by the Principal, the subject matter of the Work being as defined in paragraph 5.3 of the Work Contract;

  - Line Documentation (or also "Documentation") means documents that are prepared in accordance with the annexes to the Contract for Work, in particular attestations, certifications, declarations of conformity, documents on revisions, test reports required under the Laws for the operation of the Line; the Line Documentation also includes the Project Documentation;

  - VAT means value added tax at the rate applicable to the relevant supply at the relevant time;

  - The invoice means the basis for payment of the consideration, issued by the Agent, which will have the requirements of a tax document according to Act No. 235/2004 Coll., on Value Added Tax , as amended, and according to Section 435 of the Civil Code;

  - Warranty Period means the period defined in paragraph 16.7 of the Contract for Work;

  - Schedule means the binding dates for the performance of the obligations of the Parties agreed for the execution of the Work and its handover to the Principal in accordance with the Contract for the Work in Annex II.i Contract Schedule (including subsequent amendments made in accordance with the Contract for the Work)

  - Controlling Authority means any public authority (administrative or governmental authority and/or body in a similar capacity and/or person delegated or authorised by such authorities or bodies) which is empowered to decide on the rights and obligations and/or to control and/or review and/or assess (including sanctioning deficiencies and non-performance of obligations under the Legislation) the performance of any obligations and commitments of the Parties, in particular related to this Agreement or to determine obligations affecting the Parties generally. Controlling Authority shall always include, without limitation, the Building Authority, the provider of a subsidy granted to the Principal for the Work or any part thereof, and the bank or other financial institution through which the Agent provided the Principal with a Bank Guarantee, as well as any public authority before which proceedings related to the performance of this Agreement are being conducted.

  - Qualification requirements for the members of the Implementation Team means the minimum qualification and experience requirements for the individual members of the Implementation Team as set out in Annex 4 to this Agreement;

  - Line means the sum of all the results of the construction, assembly and technological activities for the construction of the K1 waste-to-energy line, the so-called third incinerator, which constitutes the functional unit defined in Annex A1 Overall Scope of Work of the Contract for Work, and which forms part of the Work;

  - For the purposes of this Contract, extraordinary acts are all acts not otherwise specified in the Contract performed at the request of the Principal (e.g., additional plant inspections, detailed technical studies, etc.). Extraordinary acts shall not include those acts which this Agreement or any of its Annexes contemplates or specifies the performance of, even if this Agreement or its Annexes state that the Agent shall perform the act or acts at the request of the Principal.

  - The Client means SAKO Brno, a.s., with its registered office at Jedovnická 4245/2, Czech Republic, ID No. 607 13 470. This is the designation of the Principal in the Contract for Work

  - OZ means Act No. 89/2012 Coll., the Civil Code, as amended, and/or any generally binding legal regulation replacing this Act;

  - Supporting documentation means

(a) the planning decision in force on 18 September 2021,

b) EIA - consenting binding opinion of the Ministry of the Environment dated 18 December 2020,

c) any other existing and effective documentation, not affected by the documents referred to in a) and b) above, including Permits, projects, passports, decisions, consents and documents, in particular as defined in the CA and the implementing legislation, relating to and connected with the SACO Site or the Line Construction, which gives a description of the actual condition of the SACO Site and all rights and obligations related thereto

including any updates after the conclusion of this Agreement or the Contract for Work;

  - Permits shall mean any permits, consents, approvals, certificates of authority, Public Contracts or certificates required by the Legislation and any necessary third party consents or agreements (legal actions) with such parties required for the execution of the Work, regardless of who is required by the Legislation to hold them;

  - Client's requirements means all conditions of the Client in the procedure according to the ZZVZ expressed in the Contract for Work, as amended on the date of conclusion of the Contract for Work, which are part of the Contract for Work including their annexes;

  - Worker means, in relation to a person, (i) its employees, regardless of the type of employment relationship; (ii) other workers (e.g. self-employed persons cooperating under commercial contracts); and (iii) statutory bodies or members thereof;

  - Legislation means:

- any effective generally binding legal regulation which is part of the legal system of the Czech Republic;

- relevant binding guidelines, methodologies and other regulations to which the Principal and/or the Agent is bound, provided that they are publicly available or that their existence has been announced and their content made available to the other Party;

- CSN standards or other technical standards, compliance with which is required by the documents referred to in a) and b) above for the proper execution of the Work;

- any enforceable regulation of the European Union;

- the terms and conditions of the grant received by the Principal to finance the Work or the costs associated therewith, provided that their existence has been notified by the Principal and their contents have been made available to the Agent;

  - Project Documentation means any drawings, reports, formulas, calculations, software and other documents and data relating to the design, construction of the Work, completion and operation of the Line from a construction and engineering perspective that result from the Contractor's activities under the Work Contract;

  - Handover of the Work means the activity defined in clause 16.1 of the Work Contract, which may be undertaken subject to the conditions defined in clause 16 of the Work Contract;

  - Implementation Team means the natural persons (Experts) through whom the Agent will carry out the key activities under this Agreement. The list of persons, who are members of the Implementation Team is attached as Annex 3 to this Contract, whereby only persons with the expertise listed in Annex 4 to this Contract who meet the Qualification Requirements for Implementation Team Members as set out in Annex 4 may be members of the Implementation Team, unless otherwise specified in the Contract;

  - Contract means this Assignment Agreement, including all exhibits and amendments hereto;

  - The Contract for Work means the Contract concluded between the Principal as the Client and the Contractor, the subject of which is the execution of the Work, and in view of the fact that it has not yet been concluded, the text of the Contract for Work, which is part of the tender documentation in the procurement procedure published in the Public Procurement Bulletin under the contract registration number Z2024-028031 (hereinafter referred to as the "Procurement Procedure"), forms Annex No. 1 to this Contract. 1 of the relevant concluded Contract for Work, in the version in which the Contract for Work was concluded between the Client and the Contractor, and the same shall apply to any amendments or supplements thereto; the concluded Contract for Work or amendments or supplements thereto shall become part of this Contract upon its delivery to the Agent or at the time when the Agent communicates to the Client the data for access to the electronic version of the Contract for Work placed in a place permanently accessible to the Agent; If any activities in this Contract relate to the Contract for Work prior to its conclusion, the aforementioned part of the Tender Documentation is meant and if the contents of the Contract for Work are changed during the Tender Procedure, the Principal shall inform the Agent of the current version of the Contract for Work by making it available to the extent necessary.

  - Existing Facilities (or "K2 and K3 Lines") means the K2 and K3 Lines that the Principal operates and will operate for the duration of the Work under the Work Contract;

  - Construction of the Line (or also "Construction" or "Installation") means all activities and deliveries required by the Laws and the Work Contract for the proper and timely construction and commissioning of the Line pursuant to the Work Contract, and Construction shall also include the removal of existing structures located on the SAKO Site pursuant to the Work Contract;

  - Site means the land, or a defined part of the land, including components and accessories, or structures constituting separate items, which will be used for the Line Construction, including any related activities, whereby the Site will be determined in accordance with the Contract for Work, the Supporting Documentation and will comply with the Laws;

  - SZ means Act No. 283/2021 Coll., the Building Act, as amended, and/or any generally binding legal regulation replacing this Act;

  - Conclusion of the Contract for Work means the moment at which the Agent is notified by the Customer that the Contract for Work has been signed by all parties thereto and published in the Register of Contracts, with the understanding that such parties consider it to be effective for them in respect of the obligations and rights arising for them under the Contract for Work. ;

  - Performance Tests means the tests defined in the Contract for the Work, the purpose of which is to verify that the parameters of the Work defined in the Contract for the Work, incl. Warranty Tests pursuant to Article 16 of the Contract for Work, or means tests agreed upon by the parties to the Contract for Work or the obligation to perform them resulting from a decision of the Control Authority;

  - The warranty period means that the Work will be fit for use for the agreed purpose for at least 60 months for the construction part of the Work and 24 months for the other parts of the Work and that it will maintain the agreed characteristics or achieve the performance and other values specified in the Contract. The warranty period shall commence on the date of acceptance of the Work by the Client, unless the Contract specifies a different duration of the warranty period, in particular in Annex II.h Guaranteed Parameters of the Contract for the Work

  - Contractor means the person who, on the basis of the Contract for the Work, carries out the execution of the Work

  - Trial Operation means the period defined in Article 16.2 et seq. of the Contract for the Work following the Handover of the Work, whereby the Trial Operation shall be governed by the Contract for the Work and the conditions set by the relevant Control Authority;

  - ZZVZ means Act No. 134/2016 Coll., on Public Procurement, as amended and/or any generally binding legal regulation replacing this Act;

  - VAT Act means Act No. 235/2004 Coll., on Value Added Tax, as amended.

II.

Basic provisions

- The Parties agree to enter into this Contract in accordance with the provisions of Section 2430 et seq. of the Civil Code, which shall be governed by the provisions of the Civil Code in matters not covered herein.

- The Parties declare that the information given in Article I of this Agreement is in accordance with the legal facts at the time of conclusion of the Agreement. The Parties undertake to notify changes to the data concerned in writing to the other Party without delay. The Agent declares that the bank account referred to in Article I of this Contract is a disclosed bank account within the meaning of the VAT Act. In the event of a change in the Agent 's account, the Agent shall also be obliged to provide proof of ownership of the new account by means of a copy of the relevant Contract or a confirmation from a financial institution, but the new account must be a disclosed account within the meaning of the preceding sentence. No amendment to the Contract is required for a change in the identification data of the Parties, including a change of account.

- The Parties declare that the persons signing this Agreement are authorized to do so

- The Agent declares that it is professionally competent to ensure the performance of its obligation under this Agreement.

- The purpose of the Agreement is to ensure the implementation of the Construction Manager's Activities.  For this purpose, the performance of the activities under this Contract shall be based on the Contract for Work. Construction Manager Services are the activities to be provided by the Construction Manager in accordance with this Agreement and generally binding legislation. In particular, the Construction Manager is obliged to perform for the Principal the activities set out in Annex 2 to this Agreement

- This Contract is concluded in accordance with the ZZVZ.

- The Parties declare that they will be governed by the Laws, including the application of the principle of equal opportunities, publicity and compliance with the rules of competition, in the legal relationship arising from this Agreement.

- The Agent acknowledges that the Principal expects partial financing of the Work from Modernization Fund, Modernization of Thermal Energy Supply Systems (HEAT) program within the project "Modernization of the ZEVO of SAKO Brno in order to increase the processing capacity and efficiency of operation", reg. no. 7210200001, acknowledging the terms and conditions of the subsidy in this case, as well as the Agent 's obligations to fulfil the mandatory publicity of the project in accordance with the terms and conditions of the subsidy provider and the generally binding regulations governing the provision of the relevant subsidy, whereby the Agent agrees and undertakes to provide the Principal with the necessary cooperation in this respect. The Agent declares that prior to the conclusion of this Contract it has familiarised itself with the terms and conditions of the grant within the meaning of the preceding sentence, available on the Provider's website, and that it has no objections thereto, and in this respect the Parties agree that the Principal shall continue to inform the Agent of any changes to the said terms and conditions during the term of this Contract, in which case the Agent undertakes to comply with the same.

- In the event that the Work is co-financed by the Grantor, the Agent undertakes, in accordance with the Legislation:

a)	to allow the employees or agents of the grant provider, the Ministry for Regional Development of the Czech Republic, the Ministry of Finance of the Czech Republic, the audit authority, the European Commission, the European Court of Auditors, the Supreme Audit Office, the Financial Office, the National Fund, the European Anti-Fraud Office and other authorised public authorities to enter the premises and land affected by the project and its implementation and to inspect documents related to the project,

b)	create the conditions for carrying out controls relating to the implementation of the project, provide all documents relating to the implementation of the project, enable continuous verification of the conformity of the data on the implementation of the project given in the reports on the implementation of the project with the actual situation at the place of its implementation, and provide assistance to all persons authorised to carry out controls. These authorised persons are the grant provider, the territorial financial authorities, the Ministry of Finance of the Czech Republic, the Supreme Audit Office, the European Commission and the European Court of Auditors, or other bodies authorised to carry out audits,

c)	to be kept in an appropriate manner in accordance with Act No. 499/2004 Coll., on archiving and filing services and on amendments to certain acts, as amended, and in accordance with Act No. 563/1991 Coll., on accounting, as amended, for a period of ten years after the financial closure of the project, but at the same time for at least three years after the closure of the programme in accordance with Article 88 et seq. 1083/2006, all original accounting documents, the Contract, including its amendments, and other original documents relating to the Contract, starting from 1 January of the following calendar year after the last payment for the project has been made.

III.

Subject of the Contract

- The Agent agrees to provide the Construction Manager Activities and Additional Services to the Principal until the end of the Work Warranty Period pursuant to Article 19 of the Work Contract. The Construction Manager Activities and Additional Services shall be performed:

- according to the Contract for Work, which is Annex 1 to this Contract;

- according to the Project Documentation of the Work, which is available on the Principal's profile, specifically at https://zakazky.sako.cz/contract_display_115.html;

- in accordance with the terms of the project documentation and any documentation for the project permit, acquired for the implementation of the Work, statements and binding opinions of the authorities concerned, consents of the parties to the proceedings, enforceable or legally effective decisions of public authorities and other relevant documents with which the Agent will be familiar;

- for the Construction Manager Activities to the extent and according to the terms and conditions set out in Annex 2 to this Agreement. The Principal emphasises that this is a listing of the minimum standard that the Agent is required to provide. It is therefore a demonstrative list only and it is for the Agent to identify other relevant activities necessary for the proper and timely performance of the Contract and to notify the Principal of these in an appropriate manner and without undue delay, unless they are Additional Services;

- according to other regulations and documents marked in the annexes to this Agreement;

- according to the requirements and needs of the Principal.

- The Principal agrees to pay the Agent for the performance of the Construction Manager Activity and Other Services in accordance with Article V of this Agreement.

- The Parties declare that the subject matter of the Contract is not an impossible performance and that they have concluded the Contract after careful consideration of all possible consequences

- The activities of the Construction Manager shall be carried out in their entirety by the Agent, solely through the members of the Implementation Team listed in Annex 3 to this Agreement. The members of the Implementation Team may only be changed in accordance with this Agreement.

- The Principal shall provide the Agent with the Contract for Work without undue delay after the decision on the selection of the Supplier in the Procurement Procedure. The Agent undertakes to maintain the confidentiality of all facts in the submitted documents, as well as the identity of the Contractor. This obligation of confidentiality shall cease to exist to the extent of the data ascertainable from the Register of Contracts at the time of publication of the Contract in the Register of Contracts.

IV.

Period of performance

      - The Agent shall commence the Construction Manager Activity on the basis of an invitation sent by the Principal for this purpose (the "Invitation to Commence"). The Invitation to Commence shall specify the date by which the Agent is required to commence the Construction Manager Activity. The Agent shall deliver the Commencement Notice to the Principal not later than 14 days before the date on which the Principal is required to commence the Construction Manager Activity, which date shall be specified in the Commencement Notice.

      - The activities of the Construction Manager shall be carried out in full until the date of Handover of the Work in accordance with Article 16 of the Contract for Work.

      - After the Handover of the Work, the Construction Manager shall continue to perform the Work for a period of 2 years from the date of signing of the protocol of Handover of the Work by both Parties pursuant to Article 16 of the Contract for Work.

      - The parties exclude the application of § 2440 CC. The Agent is not entitled to terminate the Contract.

V.

Fee

            - The Agent shall be entitled to any payment or other monetary consideration under this Agreement provided that the Agent has received the Invitation to Proceed. The fee for the Construction Manager's Activities shall be determined by agreement of the Parties as follows:

- The remuneration for the Activities of the Construction Manager during the period from the Conclusion of the Contract for the Work until the Handover of the Work, but no longer than 36 months from the Conclusion of the Contract for the Work, is set at 2.5% (in words: two and a half percent) of the Price of the Work excluding VAT (hereinafter referred to as the "Principal Consideration").

- The remuneration for the Activities of the Construction Manager during the period from the end of the 36-month period from the conclusion of the Contract for the Work until the date of Handover of the Work, if this occurs after such period, shall be set at 1/72 (in words: one seventy-two percent) of the Main Payment for 1 month of the duration of this Contract, but not more than a total of 3% (in words: three percent) of the Price of the Work excluding VAT (hereinafter referred to as the "Maintenance Payment").

- The remuneration for the Construction Manager's Activities during the period from the day following the Handover of the Work for the duration of the Warranty Period of the Work pursuant to Article 19 of the Contract for the Work, as well as for Extraordinary Acts, shall be determined according to the hours of activity requested, actually provided and agreed by the Principal, when

    - the remuneration for the performance of the activities of the Expert for position No. 1 in Annex 4 to this Agreement (for the expertise of the Team Leader) and the Expert for position No. 2 in Annex 4 to this Agreement (for the expertise of the Deputy Team Leader) is in the amount of:

excluding VAT		1700,- CZK for 1 hour

VAT    			357,- CZK

including VAT		2057,- CZK

    - the remuneration for the performance of the activities of the Expert at position No. 22 in Annex 4 to this Agreement (for the boiler specialty) and the Expert at position No. 28 (for the flue gas cleaning specialty) shall be in the amount of

excluding VAT		2000,- CZK for 1 hour

VAT    		420,- CZK

including VAT		2420,- CZK

    - the remuneration for the performance of the activities of the members of the Construction Manager's Implementation Team not listed in Article V(1)(a)(i) and (ii) of this Contract, whose expertise is listed in Annex 4 to this Contract, is in the amount of:

excluding VAT		1500,- CZK for 1 hour

VAT    			315,- CZK

including VAT		1815,- CZK

    - the remuneration for the performance of the activities of the Waste Energy Recovery Specialist at position No. 27 in Annex 4 to this Agreement is: ...

excluding VAT		To be added - CZK per 1 hour

VAT    			To be added ,- Kč

including VAT		To be added ,- CZK

- Compensation for the provision of Additional Services to the Principal shall be determined by the hours of provision of the Construction Manager Activity requested, actually provided and agreed to by the Principal, where the provisions of paragraph (c) of this clause shall apply mutatis mutandis with respect to the compensation for the performance of individual members of the Implementation Team.

            - The Principal Fee and the Maintenance Fee shall include all costs incurred by the Agent in the performance of its obligation under this Agreement, including any administrative fees, except for the cost of insurance pursuant to Article IX(6) of this Agreement

            - The Principal Fee and the Maintenance Fee are agreed to be the maximum allowable and apply for the entire term of the Contract.

            - In the event that the statutory VAT rate changes, the Agent shall be obliged to charge VAT at the applicable rate on top of the VAT exclusive payment. The Parties agree that in the event of a change in the amount of the consideration due to a change in the VAT rate, it is not necessary to conclude an amendment to the Contract. The Agent is responsible for ensuring that the VAT rate is set in accordance with the applicable and effective legislation

            - If the Agent incurs costs in connection with paragraph 12.6 of the Contract for Work and the Principal receives payment from the Contractor in respect of such costs incurred by the Contractor pursuant to paragraph 12.6 of the Contract for Work, the Principal shall promptly notify the Principal of such fact and reimburse the Agent for the costs pursuant to this paragraph. If the Contractor pays the costs of travel, board and lodging pursuant to paragraph 12.6 to the Agent, the Agent shall not be entitled to claim payment of these costs from the Principal.

VI.

Payment

      - The parties agree that no advances shall be made and the Agent shall not be entitled to demand payment thereof. The Parties exclude the application of Section 2436 CC. In accordance with the VAT Act, the Parties agree on partial performance. A partial performance shall be considered as a separate taxable performance carried out within the terms specified in paragraph 3 of this Article of the Contract.

      - Invoices issued by the Agent shall be the basis for payment of the consideration.

      - The parties agree that the right to payment of the Principal Consideration, or any part thereof, shall arise on the condition that the Agent has received the Invitation to commence as follows:

        - during the period from the Conclusion of the Contract for Work until the date of Handover of the Work, or until the expiry of 36 months from the Conclusion of the Contract for Work, if no Handover of the Work has taken place during this period, the Agent shall be entitled to the payment of a monthly instalment of the Principal Consideration in the amount of 1/36 (in words: one thirty-sixth) of the Principal Consideration for each month of the term of this Contract,

        - if the date of Handover of the Work occurs before the expiry of 36 months from the conclusion of the Contract for the Work, the Handover of the Work shall give rise to the Agent 's right to the remaining part of the Principal Consideration to which the Agent has not yet become entitled,

        - if, prior to the date of Handover of the Work, the Agent becomes entitled to payment of a portion of the Principal Consideration which, if billed in aggregate with previously billed portions of the Principal Consideration, would exceed the limit agreed in Article V.1(b) of this Agreement, the Agent shall be entitled to bill only that portion of such portion of the Principal Consideration which corresponds to the amount remaining until the limit agreed in Article V.1(b) of this Agreement is exhausted. After the limit agreed in Article V.1.b) of this Contract has been reached, the Agent shall not be entitled to any further payment of the Principal Consideration, and activities carried out by the Construction Manager after that point shall already be reflected in the Principal Consideration billed to date;

        - The main payment or its individual parts will always be paid on the basis of the invoice issued by the Agent and delivered to the Principal,

The Parties agree that the right to payment of the Maintenance Fee, or any part thereof, shall accrue to the Agent from the date on which 36 months have elapsed from the date of the Contract for the Work until the date of Handover of the Work, in each case for each month during the term of this Contract, when the amount of the Maintenance Fee, or the amount of the Maintenance Fee, or the amount of the Maintenance Fee, or the amount of the Maintenance Fee, shall be. V, paragraph 1, letter c) of this Contract is set at 1/72 (in words: one seventy-second) of the Main Payment, but not more than until the limit agreed in Art. V. paragraph 1, letter c) of this Contract, i.e. until the total amount that the Agent is entitled to claim for the Main Payment and the Maintenance Payment, corresponding to a total of 3% (in words: three percent) of the Price of the Work excluding VAT (hereinafter referred to as the "Limit"), and this Maintenance Payment or parts thereof shall be paid periodically on the basis of the relevant invoice. In the event that the Limit agreed in Article V, paragraph 1, letter c) of this Contract is reached pursuant to the preceding sentence, the Parties agree that the terms and conditions for the continuation of the cooperation based on this Contract (hereinafter referred to as the "Continuation Agreement") shall be negotiated between the Parties, with the Agent being entitled to make a call for the conclusion of the Continuation Agreement to the Principal not earlier than 3 months before the expected reaching of the Limit.

      - After the Handover of the Work pursuant to Article IV, paragraph 3 of this Agreement or during Extraordinary Acts or the provision of Additional Services, the Construction Manager's Activities shall be provided by the members or Additional Services of the Construction Manager's Implementation Team based on the Principal's requirements and invoiced monthly for the past calendar month, to the extent corresponding to the actual work performed pursuant to the provisions of Article IV, paragraph 3 of this Agreement. V. paragraph 1. d), e) of this Agreement, based on the invoice issued to the Principal for the amount per hours of work actually performed multiplied by the appropriate rate for each member of the Implementation Team

      - The Agent shall submit a statement with each invoice claiming payment for the activities described in Article V(1)(c) and (d) of this Agreement, which shall include a summary of the activities performed in the course of such performance, including the following:

- Specifications of the members of the Construction Manager's Implementation Team who participated in the performance of the Agent 's activities,

- the number of hours worked by members of the Construction Manager's Implementation Team,

- specification of the activities performed by individual members of the Construction Manager's Implementation Team.

      - In addition to the particulars set out in the applicable legislation for a tax document, the Agent is obliged to include the following information in the invoice:

- Contract number of the Principal, ID number of the Principal,

- subject of the Contract, i.e. the text Activities of the Construction Manager for the project "Modernization of the ZEVO of SAKO Brno" ,

- the name of the project (" Modernization of the ZEVO of SAKO Brno "/or other designation as requested by the person on the Principal's side)

- the name of the bank and the account number to which payment must be made (if the account number is different 
from the number specified in Article I(2), the Agent shall inform the Principal of this fact in accordance with Article II(2) of this Agreement),

- the due date of the invoice,

- identification of the person who prepared the invoice, including his signature and contact telephone number.

      - The due date of invoices is set by agreement at 30 days after their delivery to the Principal. The same due date shall apply to the Contracting Parties for the payment of other payments (e.g. interest on late payment, contractual penalties, compensation for damages, etc.).

      - If the invoice does not contain any mandatory or agreed particulars, if the payment or VAT is incorrectly charged, the person on the Principal's side is entitled to return the invoice to the Agent for correction before the due date. In the returned invoice, the Principal shall indicate the reason for the return or specify the reason for which the invoice is returned. The Agent shall make the correction by issuing a new invoice. Upon return of the defective invoice to the Agent, the original due date shall cease to run. The entire due date shall run again from the date of delivery of the new invoice to the Principal.

      - The Principal is entitled to inspect the invoiced works and activities. The Agent is obliged to allow authorised representatives of the Principal to carry out the inspection.

      - The Agent shall not be entitled to payment for the Site Manager's Activities during any extension of the period of performance of the Work as a result of a breach of the Agent 's obligations under this Agreement.

      - The obligation to pay the consideration (part thereof) is fulfilled on the date of debiting the relevant amount from the Principal's account.

      - The principal shall apply the institution of the special method of securing the tax 
pursuant to Section 109a of the VAT Act and shall pay the value of the performance corresponding to the value added tax stated on the invoice within the due date of this invoice set according to the Contract directly to the Agent 's personal deposit account maintained with the locally competent tax administrator in the event that

  - the bank account of the Agent intended for payment of the performance, indicated on the invoice, will not be published by the tax administrator in the "VAT register" application, or

- The Agent will be published in the "VAT register" as an unreliable payer on the date of the taxable supply, or

- The Agent will be in insolvency proceedings on the date of the taxable supply.

The Principal shall not be liable for any penalties and other sanctions assessed or determined by the tax administrator to the Agent in connection with potentially late payment of VAT, i.e. after the due date of such tax.

VII.

Rights and obligations of the Principal

            - The Principal is obliged to invite the Agent to all decisive meetings concerning the Work and its implementation, or to provide the Principal without delay with minutes or information about meetings that the Agent did not attend. This shall be without prejudice to the proper performance of the Agent 's activities within the meaning of Annex 2 to this Agreement.

            - The Principal will participate in the handover of the Site to the Contractor, the acceptance of the Work from the Contractor and the final inspection of the Work by the construction authority within the meaning of the CA with the right to decide.

            - The Principal undertakes to provide assistance to the extent strictly necessary to the Agent in securing documents, additional data, clarification of statements and opinions, the need for which arises during the performance of this Agreement. Such assistance shall be provided to the Agent within the time and to the extent agreed by both Parties or set out in Annex 2 to the Contract. The Principal undertakes to provide assistance to the Agent in such a way that there is no delay on the part of the Agent in providing the Construction Manager's Activities.

            - The Principal agrees to deliver to the Agent without undue delay after the effective date of this Agreement the Background Documentation or Documentation, or any Documentation without undue delay after the effective date of this Agreement if it has not previously been made available to the Agent or is not known to the Agent from the Principal's activities.

            - The Principal shall be obliged to issue the Agent with a power of attorney in writing upon request for the execution of matters that require the execution of legal actions on behalf of the Principal.

VIII.

Rights and obligations of the Agent

            - The Agent is obliged to:

- Provide the Construction Manager Activities in accordance with and to the extent of this Agreement and in accordance with the contents of the Work Agreement.

- Submit to the Principal for approval critical documents relating to the implementation of the Construction Manager's Activities.

- Exercise the Principal's rights under the Contract for Work to the extent of the Construction Manager's activities and in accordance with the other terms of this Agreement.

- In the performance of the Construction Manager's activities, review each instruction of the Principal and alert the Principal to any apparent impropriety in the Principal's instructions that could result in damage, promptly upon the Agent 's knowledge of such fact. In the event that the Principal informs the Agent in writing that despite the Agent 's warning the Principal insists on complying with the instructions, the Agent shall not be liable for any damage so caused.

- To hand over to the Principal without undue delay any items acquired for him in the course of his business.

- To proceed in the performance of the Construction Manager's Activities with professional care and to perform the Construction Manager's Activities on its own responsibility.

- To follow the Principal's instructions and act in the Principal's interest in the performance of the Construction Manager's activities.

- Notify the Principal without undue delay of any facts of which the Agent becomes aware or could and should have become aware and which could at the same time lead to a change in the Principal's instructions or a breach of the Contractor's obligations under the Contract for Work.

- To continuously monitor compliance with the conditions set out in the Permit and subsequent consents and decisions, including the deadlines set out therein, if the Agent is aware of such Permits and subsequent consents.

- Promptly inform the Principal of any serious circumstances relating to the execution of the Work.

- To notify the Contractor of any deficiencies in the work performed on the Work, to require the Contractor to remedy them and in the event of a threat to health or property to order the Contractor to stop performing the Work in accordance with Section 2593 of the Civil Code.

- Provide the Principal with all information, documents, etc., in writing, unless otherwise agreed with the Principal.

- Comply with the Legal Regulations and relevant statements of public authorities and organizations in the performance of the activities of the Construction Manager.

- Submit all invoices of the Contractor to the Principal for disposal within 14 days of receipt with a report verifying their accuracy.

- To grant to the Principal, without any additional payment beyond the payment agreed in Article V of this Agreement, all rights to exercise the intellectual property right, namely the exclusive, time, quantity and territorial unlimited use right and the right to exercise the intellectual property right (license according to the relevant legislation) to the outputs or other documentation that arises in the performance of the Construction Manager's Activities. The Principal shall be entitled, in particular, but not exclusively, to use, modify or supplement such outputs and documentation, to copy them, to grant a sub-licence to a third party in the full scope of the licence granted, to assign the licence to a third party in the full scope of the licence granted, to transmit the documentation to the state administration authorities or the Control Authority. The Agent grants the Licence to the Principal without the right to any additional remuneration beyond the remuneration agreed in Article V of this Agreement, i.e. the remuneration for the Licence is already part of the remuneration under Article V of this Agreement.

- The Agent is obliged to properly familiarize itself with the Contract for the Work, including all its annexes and amendments, and documentation relevant in relation to the performance of the Work so as to be able to provide the Construction Manager Activity in accordance with the Contract, prior to commencing the provision of the Construction Manager Activity. Further, the Agent shall duly acquaint itself with all documentation prepared by the Contractor under the Contract for the Work, in particular the Documentation and the Design Documents, so as to be able to properly perform the subject matter of this Contract, and at all times without undue delay after such documentation becomes available.

- The Agent shall be obliged to prepare minutes of each inspection day and to forward such minutes to the Principal without undue delay, or the Agent shall be obliged to prepare such minutes of the inspection day in electronic form, sign them electronically and send them to the Principal or to provide permanent access to the Principal and other persons who participated in the inspection day, and also to persons designated by the Principal to the Agent.

- Upon the Principal's request, the Agent shall provide the information requested by the Principal without undue delay;

- The Agent shall be obliged to attend personal meetings convened by the Principal at the Site and at a time determined by the Principal in accordance with the content of the planned meeting.

- If it is an obligation which the Principal is obliged to perform under the Contract for Work and the Agent is obliged to perform such obligation under this Contract, then the Agent shall deliver the output by which such obligation is to be performed to the Principal no later than 5 working days before the expiry of the time limit set for the Principal in the Contract for Work to perform such obligation.

- The Agent shall perform other services and Extraordinary Acts as requested by the Principal, unless the Principal rejects the request in writing within 10 days after receiving the request.

            - The Agent undertakes not to disclose to third parties any information of which it has become aware in connection with the performance of the subject matter of the Contract or which is the subject matter of this Contract and/or the Contract for Work and which cannot be obtained from public sources, as described in more detail in particular in Article XV. paragraph 1 of this Contract (hereinafter referred to as "Protected Information"), unless it is necessary for the proper performance of this Contract, provided that the Agent is entitled to disclose such information only to the  necessary

    - third parties involved in the Agent's performance under this Agreement, but whom the Agent is contractually obligated to maintain confidentiality with respect to the Protected Information to the same extent that the Agent is obligated to maintain such confidentiality,

    - Control Authorities, which, however, the Agent is obliged to notify of the nature and scope of the Protected Information and the fact that the Principal does not wish to disclose it to third parties and requests its protection.

            - The Agent may not assign its rights and obligations under the Contract to a third party without the Principal's consent, without prejudice to the Agent's right to perform the Contract through subcontractors, in particular members of the Implementation Team.

            - The Agent may deviate from the Principal's instructions only if this is urgently necessary in the Principal's interest and if the Principal's consent cannot be obtained in time. However, in no case may the Agent deviate from the instructions if this is prohibited by the Contract or the Principal.

            - In the event that the Agent discovers a serious OHS violation on the Site that poses an immediate threat to the lives and health of persons or that may adversely affect the execution of the Work or the operation of the Principal's Existing Facility, the Agent shall immediately notify the Construction Manager or other responsible person of the Contractor pursuant to the Laws and request that the Work be suspended or that corrective action be taken immediately.

            - In the event that it is necessary to take any legal action on behalf of the Principal in the performance of the Agent's obligations under this Agreement, the Agent shall promptly inform the Principal thereof, provide the Principal with all necessary information about such legal action and prepare a draft of a special power of attorney for such legal action. The Agent shall not be authorised to take any legal action on behalf of the Principal (i.e. to negotiate rights for the Principal and to bind the Principal to obligations in relation to third parties) without the express prior written authorisation by the Principal for each such individual case of representation or if such authorisation is provided for in this Agreement.

            - In the event that the Agent discovers that any of the documents, documents or other performances provided to it under this Contract is defective or contains a defect, or could and should have discovered such a defect, the Agent shall be obliged to notify the Principal and the Contractor of such defect or defects without undue delay whenever the Agent discovers or could and should have discovered such defect or defects and shall propose to the Principal within the same period of time appropriate measures to eliminate such defect.

            - The Parties agree that the Agent shall perform all of its obligations under this Agreement and its annexes in a timeframe appropriate to ensure the smooth execution of the Work under the Work Agreement, taking into account the Schedule in particular. The Principal may, in justified cases, unilaterally set a deadline for the Agent to fulfil a specific obligation. In the event that the Agent is objectively unable to fulfil the obligation within such time limit, the Principal must inform the Client without delay, justify why it is unable to fulfil the obligation within the required time limit and inform the Client within what time limit it will fulfil the obligation.

Unless the Parties otherwise agree on a time limit for the performance of a specific obligation and unless such time limit is specified by the Principal pursuant to the preceding sentence, it shall be deemed a reasonable time limit for the performance of such obligations:

- Inspection of the Project Documentation - the Agent is obliged to inspect the relevant documentation submitted by the Contractor within 21 days from the date of submission of the relevant documentation or part thereof, and within this period he is also obliged to inform the Principal with the result of the inspection carried out by him, including the preparation of a report on the inspection carried out, so that no later than within 28 days from the date of submission of the relevant documentation to the Agent, the comments can be submitted to the Contractor for their incorporation in accordance with the Contract for Work

- Inspection of the implementation and compliance with the Documentation - shall be carried out by the Agent on an ongoing basis, whereby the Principal must respond to a specific request from the Principal within 7 days from the date of receipt of the request, and within this period is also obliged to inform the Principal in writing with the result of the inspection carried out by him.

- Change Procedures/Proposal Review - The Agent shall review the relevant Documentation and present the result of its review to the Principal within 7 days of receipt of the request by the Contractor or Principal. Following the Principal's review, the Agent shall process the Principal's requirements without undue delay, so that the Principal is not in default of its obligations under the Contract for the Work, in particular the obligations set out in Article 27 of the Contract for the Work.

- Handover procedure - according to the terms set out in the Contract for Work.

- Inspection of the provision of the permit of the plan - will be carried out by the Agent on an ongoing basis, whereby the Principal must respond to a specific request from the Principal within 7 days from the date of receipt of the request, and within this period is also obliged to inform the Principal in writing with the result of the inspection carried out by .

- Check of compliance with the Legal Regulations - shall be carried out by the Agent on an ongoing basis, whereby the Principal must respond to a specific request from the Principal within 7 days from the date of receipt of the request, and within this period is also obliged to inform the Principal in writing with the result of the inspection carried out by him. Other deadlines required by the Principal, which must be observed by the Agent throughout the execution of the Work, are set out in Annex 2 to the Contract.

            - Reports on other milestones met under the Contract for Work or based on requirements of the Controlling Authorities (e.g., funding provider or subsidy) or based on the Annexes to this Contract shall be prepared and submitted to the Principal no later than 5 days after receipt of the relevant report under this Contract, and samples of such documents are provided in Annex 2 to this Contract. The Parties agree that office and resting facilities for the Agent´s Implementation Team and personnel visiting the Agent on site shall be provided by the Agent within its scope of work at a location reserved by the Principal. All necessary equipment for the Agent's activities shall be provided by the Agent itself, within its scope of work, both at the construction site and at other facilities of the Agent.

            - The Agent is not entitled to:

- to change the content of the concluded Contract for the Work, including annexes and related documents (e.g. the content of concluded insurance relations, the text of bank guarantees, etc.) between the Principal and the Contractor, or to change the content of contractual relations with other entities involved in the proper implementation of the subject of the Work (a change is understood as an addition, refinement or modification of the contractual relationship);

- accept the Contractor's opinions regarding the eligibility, amount, method and timing of payments to the Contractor;

- decide whether or not to apply the Principal's contractual sanctions against the Contractor;

- assert the Principal's claims for withdrawal from the Contract for Work or take actions eliminating such claims;

- decide on the extent of the Principal's claim under the Contract for Work;

- to decide on the approval and termination of tests prior to the Handover of the Work;

- decide on the acceptance of the Work by the Principal;

The above cases mentioned in this paragraph limit the Agent´s independent negotiations with the Contractor. The Agent's actions in question shall always require the prior written consent of the Principal. In such cases, the Agent shall propose a solution in writing to the Principal, giving reasons for its position and evaluating in detail the consequences of accepting the proposed solution. In the event of acceptance of the Agent's proposal by the Principal, the Agent shall be fully responsible for the consequences of such acceptance.

IX.

Liability, insurance

- Liability for damages shall be governed by the relevant provisions of the Civil Code, unless the Contract provides otherwise.

- The Agent shall be liable for damages incurred by the Principal as a result of defective performance in full, including any non-pecuniary damages. Damage shall also be deemed to be damage which the Principal has incurred by having to incur costs as a result of the Agent's breach of duty

- The parties agree that the second sentence after the semicolon of Section 2434 CC shall not apply and expressly agree that any act or omission of a third party, even if authorised with the Principal's consent, shall be deemed to be an act or omission of the Agent, including any liability arising therefrom, with the Agent being liable as if it had carried out the activity itself.

- The Agent undertakes to take out professional insurance at its own expense for the entire period of performance of its obligations under this Agreement, as well as for the entire duration of the obligations arising from this Agreement, with a limit of indemnity for a damage event of at least CZK 30,000,000.

- The activities of the Construction Manager are covered by insurance arranged by the Principal, namely construction and installation insurance and liability insurance. Details of these insurances are set out in Annex II.f of the Contract for the Work. The cost of the insurance shall be borne by the Principal. The Agent shall provide the Principal with all necessary assistance regarding this insurance.

- The Agent undertakes to provide the Principal with all necessary assistance in the event of an insurance claim

- Breach of insurance obligations is a material breach of this Agreement

X.

Sanctioning arrangements

- In the event that, despite the Principal's notice, the Agent is in default in fulfilling its obligation under Article IX, paragraph 4, the Agent agrees to pay the Principal a contractual penalty of 0.03% of the Principal Consideration under Article V, paragraph 1, letter b) of this Agreement for each day of delay in fulfilling this obligation

- In the event of breach of obligations which this Agreement does not provide for contractual penalties by separate arrangements, or in the event of the Agent's delay in fulfilling its obligations within the time limits set out in this Agreement (in particular in Article VIII, paragraph 8 and in Annex 2 to this Agreement), the Agent shall be obliged to pay the Principal a contractual penalty of 0.03% of the Principal Consideration excluding VAT set out in Article V, paragraph 1, letter b) of this Agreement for each individual breach of an obligation or for each day of delay in fulfilling such obligation.

- In the event that, despite the Principal's notice, the Agent is in default in the performance of its obligations under Article XV, paragraphs 3, 4, 5 and 6 of this Agreement, the Agent agrees to pay the Principal a contractual penalty of 0.05% of the Principal Consideration excluding VAT specified in Article V, paragraph 1(b) of this Agreement for each day of delay in the performance of such obligations.

- In the  that the Agent, due its own fault, in particular by failing or violating an obligation arising from this Contract or its annexes, causes an extension of the specified total time of performance under the Contract for the Work (the time limit for the Construction of the Work), it shall pay the Principal a contractual penalty of 0.3% of the Principal Consideration excluding VAT specified in Article V. paragraph 1 letter b) of this Contract, for each day of extension of the time limit for the execution of the Construction under the Contract for the Work

- If the Agent breaches the obligations set out in Article XII. of the Contract, the Principal shall call upon the Principal to cease the breach of obligations. If, even after such notice, the breach of such obligations is not terminated within 7 days of the date of receipt of such notice by the Principal, the Agent shall pay to the Principal a contractual penalty of 0.015% of the Principal Consideration, excluding VAT, referred to in Article V.1(b) of this Contract.

- In the  events that the Agent gives an instruction in contravention of the principles of occupational health and safety as set out in this Agreement, its Annex 2, the Contract for Work (in particular its Annex B2 Health, Safety and Environmental Requirements) or the relevant legal regulations governing the principles of occupational health and safety, the Agent undertakes to pay the Principal a contractual penalty of 0.1% of the Principal Consideration excluding VAT set out in Article V.1(b) of this Agreement for each such individual instruction.

- In the  events that the Agent fails to remedy defects in the performance, which is the subject of the Construction Administrator's Activities, within the time limit pursuant to Article VIII, paragraph 7 of this Agreement, the Agent undertakes to pay the Principal a contractual penalty of CZK 1,250, excluding VAT, for each day of delay in the performance of this obligation.

- If the Agent fails to perform the Construction Manager's Activities in  with the provisions of this Agreement and the Principal incurs damage as  result (e.g. by paying penalties imposed by the relevant administrative authorities), the Agent shall be obliged to pay the Principal the full amount of such damage, without prejudice to the limitation of damages in Article X(11) of this Agreement.

- In the event of delay in payment of the consideration, the Parties agree on statutory interest on late payment.

- The total amount of the contractual penalties that the Principal is entitled to demand from the Agent shall not exceed an amount corresponding to 20% of the Principal Consideration excluding VAT specified in Article V. paragraph 1 letter b) of this Agreement.

- The agreed contractual penalties shall be paid by the obligated party regardless of fault and regardless of whether and in what amount the other party suffers damage. Compensation for damages (injury) may be recovered to the extent that the damage exceeds the contractual penalty. The total amount of damages shall not exceed an amount equivalent to 3 % (three percent) of the Price of the Work excluding VAT.

- The total amount of contractual penalties and damages shall not exceed in total an amount equivalent to (three percent) of the Price of the Work excluding VAT.

- If an obligation of either Party under this Agreement is terminated prior to its proper termination, the right to liquidated damages shall not be extinguished if it was created by an earlier breach.

- The termination of an obligation under this Agreement by its late performance shall not extinguish the right to a contractual penalty for late performance.

XI.

Termination of the Contract

      - The Agent acknowledges that this Contract can only be executed the Contract for the Work is concluded and executed, and an extension of the time for the execution of the Work cannot be excluded. If

(a) the Contract for the Work is not executed within 12 months of the effective date of this Agreement; or

b) the Agent fails to conclude a Continuation Agreement within 3 months of the Principal's justified request pursuant to Article VI, paragraph 3, last sentence of this Agreement

either Party shall be entitled to terminate this Agreement without notice

      - In the  that the Contract for Work is terminated without completion of the entire Work (i.e., for example, termination of the Contract for Work or withdrawal from the Contract for Work), the Principal shall be entitled to terminate this Contract at its discretion without notice.

      - In the event of termination of this Agreement pursuant to paragraph 1 or 14 of this Article, the Agent shall not be entitled to compensation for any damages (whether actual damages or lost profits), unless otherwise expressly agreed in this Agreement.

      - In the  of termination of this Agreement pursuant to paragraph 2. of this Article, the Agent shall be entitled to reimbursement of reasonable and justifiable costs incurred on the part of the Agent, consisting in the costs of the activities of persons appointed to the Implementation Team, incurred on the basis of employment law, which the Agent incurred in connection with the performance of this Agreement, even after the termination of this Agreement, however, not to exceed the extent of the claims of such persons directly provided for by law in connection with the termination of their dependent activities for the Principal, provided that the Agent shall terminate their activities without undue delay after the termination of this Agreement, which the Agent undertakes to do, and no claims of such persons agreed to be broader than those expressly provided for by law or arising from the Agent's delay in terminating the activities of such persons shall be compensated.

      - In the event of termination of the Contract pursuant to paragraph 1 or 2 of this Article, the Agent shall be entitled to the remuneration to which it was entitled up to the time of termination of this Contract as a result of the termination referred to therein, provided the Agent shall be entitled to all that has been paid to it to date in  of any remuneration pursuant to Article V(1) of this Contract. For the avoidance of doubt, it is agreed that the Agent's invoices for the period following termination shall also comply with the requirements set out in Article VI. Agreement and shall be subject to the rules set out therein.

      - A Contracting Party shall be entitled to withdraw from this Agreement if there is a material breach by the other Contracting Party which has been notified of the breach in a notice to remedy such breach (hereinafter referred to as the "Notice to Remedy") and the consequences of the breach have not been remedied even within a reasonable period of time specified in the Notice to Remedy, or if the breach has consequences which cannot be remedied

      - In particular, the Parties consider the following breaches of contractual obligations to be a material breach of the Contract:

        - delay of the Principal in payment of the amount due for more than 60 days;

        - The Agent proceeds with the provision of the Construction Manager Activity in a manner that is manifestly inconsistent with the agreed manner and scope of provision of the Construction Manager Activity and/or the Construction Manager Activity is provided in contravention of this Agreement in such a way that deadline for the Handover of the Work is or has been missed.

      - In the event of early termination of the Contract, i.e. before the Agent's obligations under this Contract are fulfilled, the Agent undertakes to provide the Principal with all necessary assistance to enable the Principal or a person authorised by the Principal to ensure the performance of the activities of the construction manager in due and timely manner under normal conditions. The remuneration for such assistance, if performed prior to the termination of the Contract, shall be part of the remuneration for the Construction Manager's activities pursuant to Article V of this Contract, after the termination of the Contract the Agent shall not be entitled to any remuneration for such assistance.

      - At the  of termination of the Contract, the Agent undertakes to prepare a final report and to submit it to the Principal without undue delay and further to advise the Principal in writing of any measures that need to be taken within a reasonable time after termination of the Contract to ensure that the performance of the Work is not disrupted/hampered or of any measures that need to be taken to avert any imminent risk of damage as  result of the Agent´s failure to complete its activities under this Contract. The remuneration for such activity, if performed prior to the termination of the Contract, shall form part of the remuneration for the Construction Manager's activities under Article V of this Contract, after the termination of the Contract the Agent shall not be entitled to any remuneration for such activity.

      - The termination of the Contract shall not affect those provisions of the Contract from which this fact follows or in which this is expressly stated (e.g. liability for damages, contractual penalties, etc.), Article XI. XI of the Contract shall continue to apply at all times after termination of the Contract.

      - Upon termination of this Agreement, or at any other time at the request of Principal, Agent shall promptly return to Principal all property and documents containing or constituting information or creations belonging to Principal, including any copies made by Principal or others.

      - Without undue delay after termination of the Agreement, the Agent shall return to the Principal all items and documents received from the Principal in  with the provision of the Construction Manager Activities.

      - The Parties may withdraw from this Contract in the cases agreed in this Contract or provided for in the CC

      - The Principal shall be entitled to terminate this Agreement without notice if the Agent is in default for more than 10 days in fulfilling the obligation under Article XV, paragraph 4 of this Agreement. In the event of termination pursuant to the preceding sentence, the provisions of paragraph 4 or 5 of this Article shall not apply. Nor shall the provisions set out in Article X of this contract apply.

XII.

Social and environmental responsibility, innovation

- The Principal requires the Agent to provide the Construction Manager Activity in  with the International Labour Organization (ILO) Conventions adopted by the Czech Republic.

- The Agent undertakes to comply with at least the following basic working standards:

- Convention No 87 on Freedom of Association and Protection of the Right to Organise

- Convention No. 98 on the right to organise and to bargain collectively

- Forced Labour Convention No. 29

- Convention No. 105 concerning the Elimination of Forced Labour

- Convention No. 138 on minimum age

- Convention No. 182 on the Worst Forms of Child Labour

- Convention No 155 concerning the safety and health of workers and the working environment

- The Agenl is responsible for ensuring that all employees involved in the provision of the Construction Manager's Activities have the legal right to work in the Czech Republic and that their employment complies with Act 262/2006 Coll., the Labour Code.

- The Agent must ensure equality and fair and dignified treatment of all its employees by encouraging diversity, innovation and fairly rewarding its employees. Discrimination against employees of any kind is strictly prohibited.

- All recruitment in the provision of the Construction Manager Activity shall be carried out by the Agent on a systematic basis respect, to  extent possible, the Principal's preference to provide employment to suitably qualified local candidates where possible. The Agent also agrees not to make any offers of employment to existing employees of the Principal. The Agent is further expected to respect fundamental human rights, including compliance with the Universal Declaration of Human Rights and the European Convention on Human Rights.

- If the Principal becomes aware that the Agent is not in compliance with the above regulations, the Agent shall remedy such deficiencies and complete performance under the Contract in  with such requirements. Any potential costs associated with this obligation shall be the Agent's expense.

- The Agent undertakes, to the  extent possible, to adhere to the principles of socially responsible procurement, environmentally responsible procurement and innovation in the provision of Construction Manager Activities. In  sense, the Contractor undertakes to comply with all labour, occupational health and safety and  regulations.

XIII.

Dispute Resolution

- If an ambiguous term or unclear provision appears in the Contract, its Annexes or any Appendices, the Parties shall enter into good faith negotiations to reach an agreement.

- In the event any dispute or difference of opinion between the Principal and the Agent relating to or arising out of  Contract, the Parties undertake to use their best efforts resolve such disputes amicably between the representatives of the Parties referred to in Article 1 of the Contract.

- If the Parties fail to resolve their disputes by mutual negotiations at the level of representatives of the Parties within 28 days from the date of commencement of negotiations, each Party shall be entitled to give written notice to the other Party. This notice shall state that a dispute exists, the grounds for the dispute and a proposal for the resolution of the dispute.

- If the dispute is not settled in accordance with the preceding clause within 42 days of the date of the written notification to the other Party pursuant to the preceding clause, the Party concerned shall be entitled to institute proceedings in a court of competent jurisdiction to resolve the dispute. The Parties agree that the court of competent jurisdiction shall be the court of the Principal's registered office. The Parties also agree that the valid and effective provisions of the legal system of the Czech Republic shall apply to the proceedings in the court referred to in the previous sentence of this paragraph. The subject matter and local jurisdiction of the court and the procedural rules for such proceedings are also agreed in the event that the Parties do not proceed in accordance with this and the preceding paragraph of the Agreement   in resolving disputes.

- In view of the fact that the mutual relations between the parties under and in  with this Agreement are of a commercial nature, the parties to this Agreement shall, pursuant to Section 89a of Act No. 99/1963 Coll. agree that in matters where the District Court has jurisdiction in the first instance over disputes between the Parties, the Municipal Court in Brno shall have jurisdiction in the first instance, and in matters where the Regional Court in Brno has jurisdiction in the first instance over disputes between the Parties, the Regional Court in shall have jurisdiction in the first instance.

- The provisions of this Article shall not affect the rights of the Parties under the Law.

XIV.

Delivery, authorized persons for communication and negotiations under the Contract

- All documents delivered under or in  with this Contract between the Parties shall be in the Czech or Slovak language; between the Agent and the Contractor in the Czech or Slovak language, and shall be delivered by one of the following methods:

- data mailbox;

- by personal delivery of the document;

- by email with a guaranteed electronic signature; or

- delivery by post or courier;

If the Contract for Work provides for a different method of communication, the contents of the Contract for Work shall be binding for the Agent when communicating with the Contractor.

- Letters will be delivered to the Principal to the persons and address set out below:

Address:	[as registered in the Commercial Register]

Email: 	[pavel.slezak@sako.cz]

To your hands: 	[Ing. Pavel Slezák, Ph.D.]

- Letters shall be delivered to the Contractor of the Work to the persons and at the address communicated by the Principal to the Agent no later than with the execution of the Contract for the Work, to the extent:

Address:	[To be added]

Email: 	[To be added]

To your hands: 	[To be added]

- Letters will be delivered to the Agent to the persons and address set out below

Address:	[as registered in the Commercial Register]

Email: 	[strmiska@bkom.cz]

To your hands: 	[Ing. Jan Strmiska]

- Any document will be deemed to have been delivered:

  - if it is delivered by a Contracting Party by means of a data box at the time of logging into the data box by the other Contracting Party after delivery of the message or at 10.00 a.m. on the next working day after delivery of the message to the data box of the other Contracting Party, whichever is earlier;

  - if the document is served by personal delivery, at the moment when the addressee's representative (the other party) confirms receipt of the document, or at the moment when the addressee's representative refuses to accept the parcel;

  - if it is delivered by email with a guaranteed electronic signature, at the moment when the email was sent to the email address of the other party, while if the email was sent outside a working day or after 4 p.m. on a working day, the moment of delivery of the email shall be considered to be 10 a.m. on the following working day;

  - if it is delivered by post or courier service at the moment when the representative of the other party has received the consignment, or at the moment when the addressee's representative has refused to receive the consignment.

- Both the Principal and the Agent are entitled to change the delivery details, with the  details agreed for the Contractor being determined and changed by the Principal. In the event of a change, the other party shall be obliged to deliver according to the newly specified data at the time of notification of the change. The provisions of Article XIV, Paragraph 5 of the Contract shall apply mutatis mutandis to the notification of a change pursuant to Article XIV, Paragraph 6 of the Contract.

- The persons named in the header of this Contract for each of the parties hereto, with reference to this paragraph of the Contract, shall at all times be entitled to act for the parties in the performance of this Contract and to communicate, except for those persons for whom it is required by law to do so, without the necessity of proving their authority, each individually. Any change thereof shall be communicated between the Parties in accordance with the procedure set out in Article XIV(6) of the Contract

- Amendments to this Agreement, as well as acts directly leading to its termination, may only be performed on behalf of the Parties by the statutory bodies of the acting Party, unless they authorize a third party to do so.

XV.

Special Arrangements

- The obligations set forth to protect the Principal's information that is a trade secret or confidential information of the Principal shall survive the termination of the obligation under this Agreement. All information that is expressly designated as such as "Confidential" or is of such a nature that its disclosure may cause harm to a party to this Agreement, regardless of whether it is personal, commercial or otherwise, is designated as Confidential by the Parties. The only information that shall not be considered Confidential is information that is publicly available or has been published by the other Party. Such information or documents may not be used by the other Party for any other purpose. If the breach of these obligations results in damage, the Party that committed the breach shall be obliged to compensate the other Party for the damage suffered. This does not apply to information that the Principal is obliged to provide under applicable law.

- The Agent undertakes to provide all necessary cooperation for the performance of financial control within the meaning of Act No. 320/2001 Coll., on Financial Control in Public Administration and on Amendments to Certain Acts (Act on Financial Control), as amended, and Act No. 255/2012 Coll., on Control (Control Regulations), in connection the performance of the subject matter of this Agreement.

- The Agent shall be obliged to perform the Construction Manager Activities throughout the duration of the Contract in such a way that any performance towards the Contractor, the Principal or the Controlling Authorities shall be the result of the activities of those members of the Implementation Team whose expertise, as expressed in the column "Expertise of the Implementation Team Member" in Annex 4 to this Contract, corresponds to the nature of the performance in question and who have been approved by the Principal in accordance with the procedure under this Contract

- The Parties have agreed that the Implementation Team has already been assembled by the Agent as of the date of conclusion of this Agreement, and the list of members of the Implementation Team is set out in Annex 3 to the Agreement. By signing this Agreement, the Principal also approves the members of the Implementation Team. Attachment 3 of the Contract has not been completed as of the date of this Contract, and the Agent agrees to nominate all persons for the position of No. 27 "Energy Recovery Specialist" within 30 days of the effective date of the Contract for the Work. Within the same period of time, the Agent shall provide the Principal with documents confirming the fulfilment of the Qualification Requirements for the Implementation Team Member for the position of No. 27 "Waste Energy Recovery Specialist" as defined in Annex 4 of the Contract, namely at least proof of professional competence, if required by the Law for the position of the Implementation Team Member, and a professional CV demonstrating the fulfilment of the education and experience requirements, if required for the position in Annex 4 of the Contract. The Principal shall give its written approval to the proposed persons for the position of No 27 "Waste to Energy Specialist" within 15 days of receipt of the proposal and the documents referred to in the previous sentence. Upon the issuance of the consent or the expiry of the deadline, the person concerned shall become a member of the Implementation Team. The Principal may not refuse to consent to a member of the Implementation Team if the documents identified above are submitted to it by the Agent. The Principal may grant consent to a proposed member of the Implementation Team even if that proposed member does not meet the requirements set out in Annex 4

- The Agent shall be entitled to replace a member of the Implementation Team provided for in this Contract during the term of this Contract only for compelling reasons and only with the prior written consent of the Principal. The new member of the Implementation Team must meet the Qualification Requirements for members of the Implementation Team set out in Annex 4 to the Contract, of which the Agent shall provide evidence together with the request to change the member of the Implementation Team. Sufficient evidence shall be deemed to include: evidence of professional competence, if required by law for the position of Implementation Team member; and a professional CV demonstrating compliance with the education and experience requirements, if required for the position in Annex 4 to the Contract. The Principal shall give written consent to the change within 15 days of receipt of the request, at which point the person concerned shall become a member of the Implementation Team and replace the original person. The Principal shall not refuse to consent to the change of the member of the Implementation Team if the relevant documents are submitted to it by the Agent. The Principal may consent to a new member of the Implementation Team even if the new member does not meet the requirements set out in Annex 4.

- The Agent is obliged to replace a member of the Implementation Team at the Principal's request if there has been a serious or repeated breach of the Agent's obligations as a result of the actions or omissions of such member of the Implementation Team. Replacement pursuant to this paragraph shall be made by the Agent proposing to the Principal a new person who meets the Qualification Requirements for Implementation Team Members set out in Annex 4 without undue delay after the Principal's request is received by the Agent, but no later than one month after the Principal's request is received by the Agent. In approving the new person, the Principal and the Principal shall proceed in accordance with paragraph 5 of this Article of the Agreement. The Agent shall ensure that the original person does not participate in the performance of the Construction Manager Activities under this Agreement after receiving a reasonable request pursuant to the first sentence of this paragraph and, until a new person is approved by the Principal in his place, shall take appropriate measures to ensure the proper performance of the Construction Manager Activities performed by the person whom the Principal has requested to be replaced pursuant to the first sentence of this paragraph.

- The Agent and the Principal assume at the conclusion of this Contract that they meet the conditions of Section  of the ZZVZ (hereinafter referred to as "vertical cooperation"). The Agent undertakes to act during the term of this Contract (or in all and any other cases that have or may have an impact on the maintenance of the conditions of vertical cooperation) in such a way that the conditions of vertical cooperation dl Section 11 of the ZZVZ remain maintained.

XVI.

Final arrangements

- This Agreement may be amended or supplemented by the Parties only in the form of written amendments, which shall be numbered in ascending order, expressly declared to be an amendment to this Agreement and signed by authorized representatives of the Parties.

- The Contract shall enter into force upon signature by both Parties. This Contract shall become effective upon publication in the Register of Contracts pursuant to Act No. 340/2015 Coll., on Special Conditions of Effectiveness of Certain Contracts, Publication of Such Contracts and on the Register of Contracts (the Register of Contracts Act), as amended. The Agent expressly consents to the publication of this Contract in the Register of Contracts, and the Contract shall be sent for publication by the Principal.

- The Parties agree that the Agent expressly consents to the disclosure of the contractual terms and conditions contained in this Agreement to the extent and under the terms of generally binding legal regulations.

- The contract is drawn up in four copies with the validity of the original, with the Principal receiving two copies and the Agent receiving two copies.

- By signing the Contract, the Parties agree to exclude the application of the provisions of Section 557 and Section 1805(2) of the Civil Code.

- For the avoidance of doubt, the Agent expressly confirms that it is a business, concludes the Contract in the course of its business and the provisions of Section 1793 CC shall therefore not apply to the Contract.

- If any part of this Contract becomes invalid or if performance under this Contract becomes impossible, the Parties shall thereafter be bound by the remainder of this Contract, unless the content of the obligation or the purpose of the Contract indicates that the remaining performance is not meaningful to the Principal.

- The Parties do not wish any rights and obligations beyond the express provisions of the Contract to be inferred from past or future practice established between the Parties or customary practices generally or in the industry relating to the subject matter of the Contract, unless otherwise expressly agreed in the Contract.

- The Parties declare that they have read this Contract before signing it, that it is concluded after mutual negotiation according to their true and free will, definitely, seriously and understandably, not under duress or under clearly disadvantageous conditions, and that they have agreed on its entire content, which they confirm by their signatures.

- The following annexes form an integral part of the Agreement:

Annex No. 1: Contract for the Work according to the Definition of the Contract for the Work

Annex 2: strategy

Annex 3: Specification of the persons who will be responsible for the performance (Implementation Team)

Annex 4: Qualification requirements for members of the Implementation Team

| Principal: In Brno on ................ |  | Agent: In Brno on .................. |
| --- | --- | --- |
| _______________________________ |  | _______________________________ |
| SAKO Brno, a.s. Ing. Pavel Urubek Chairman of the Board of Directors |  | Brněnské komunikace, a.s. Ing. David Grund Chairman of the Board of Directors |
| _______________________________ |  | _______________________________ |
| SAKO Brno, a.s. Ing. Daniel Struž, MBA Vice-Chairman of the Board of Directors |  | Brněnské komunikace, a.s. JUDr. Michal Marek Vice-Chairman of the Board of Directors |