Informative translation

Modernization of ZEVO of SAKO Brno

Annex 2 to the Contract

Project strategy

Brno Communications a.s.

Renneská třída 787/1a, 639 00, Brno - Štýřice

- Table of Contents

1.	Introduction	1

2.	Project description	2

3.	Project objective	3

4.	List of abbreviations	4

5.	Definition of	6

6.	Control of project risk management	7

7.	Specification of activities of individual members of the construction manager team	14

8.	Project documentation management system	23

9.	Project Scope Control	25

10.	Time control in the project	27

11.	Cost Control in the Project	28

12.	Quality Control	29

13.	Checking that the environmental requirements of the project are met	32

14.	Health and safety inspection in the project	33

15.	Project documentation control	34

16.	Control of construction and delivery	38

17.	Commissioning process	41

18.	List of tables	44

19.	Attachments	45

# Introduction

The detailed strategy of the project "Modernization of the ZEVO of SAKO Brno" is a document in which the Construction Manager describes the setup of the organizational and management structure in relation to their staffing to fulfill the role of the Construction Manager on the project.

Key strategic areas are defined in the project strategy and described in individual chapters.  In particular, the strategy focuses on the establishment of organisational and communication relationships, outlines the structure of the Construction Manager team and the individual activities involved in performing the Construction Manager role.

The basic services of the Construction Manager are divided into two main chapters:

- Project Management

- Technical consultancy and technical supervision

These basic chapters are further subdivided into more specific services:

Project Management

- Control of project risk management

- Control of the Contractor's documentation management system in the project

- Project scope control

- Time control in the project

- Cost control in the project

- Quality control

- Checking the security of environmental requirements in the project

- Health and safety inspection in the project

Technical consultancy and technical supervision

- Control of project documentation

- Control of procurement and acceptance

- Delivery control

- Control of construction

- Commissioning control

- Inspection of the handover of the work

- Checking the operation of the work during the warranty period

# Project description

The project includes a complete and final waste-to-energy plant, the K1 line using mixed municipal waste and selected industrial waste, including design, fabrication, installation, testing and commissioning. The client's existing facility, consisting of the K2 and K3 lines, will remain in continuous operation, receiving and processing waste seven days a week, throughout the duration of the works. The client operates the existing facility and will be the operator of the line after its construction. The design, construction, testing and commissioning of the line shall be planned and executed as far as possible without disrupting the operation of the Customer's existing facility.

# Project objective

The aim of the project is to build a new K1 line, which is a highly efficient renewable energy cogeneration facility and to provide an energy, economic and environmental solution for residual municipal waste in the wider region.

# List of abbreviations

| AD | Author's supervision |
| --- | --- |
| As Built | Documentation of the actual condition for DPS (As Built) |
| OHS | Health and safety at work |
| CZT | Central heat supply |
| CSN | Czech technical standard |
| CSN EN | Adopted European standard |
| CSN EN ISO | Adopted international standard |
| DNU | Documentation for necessary modifications |
| DOS | Documentation for building notification |
| DPP | Supplier's code for operation |
| DPPP | Documentation of professional project documents |
| DPU | Supplier's Maintenance Code |
| DS | Transport constructions |
| DSP | Documentation for project authorisation |
| DSPS | Documentation of the actual construction |
| DSP | Documentation of staff training |
| DUP | Documentation for commissioning |
| DUR | Documentation for planning decision |
| DZ | Documentation of the project |
| DZS | Documentation for the construction assignment |
| EIA | Environmental Impact Assessment |
| EL | Wiring |
| EPS | Electric fire alarm system |
| HMG | Schedule |
| ID | Engineering activities |
| JD | Single-stage merged documentation |
| KD | Control day |
| KV | Comprehensive testing |
| KZP | Control test plan |
| MaR | Measurement and control |
| MD | Assembly documentation |
| MP | Methodological aid |
| NN | Low voltage |
| NV | Government Regulation |
| PBŘ | Fire safety solutions |
| PBZ | Fire safety equipment |
| PDPS | Documentation for the implementation of the construction |
| PGT | Guarantee test project |
| POV | Plan of the construction organisation |
| PPN | First Hire Project |
| PS | Operating file |
| PTD | Accompanying technical documentation |
| RDS | Implementation documentation of the construction |
| Red Correct | Corrected documentation of the actual state (Red Correct) |
| RFA | Budgetary and financial analysis of the contract |
| RP | Regulatory plan |
| SD | Construction diary |
| SO | Building object |
| SoD | Contract for Work |
| SP | Feasibility study |
| SpSt | Construction manager |
| SZ | Act No. 283/2021 Coll., as amended - Building Act |
| TD | Technical supervision of the builder |
| TP | Technological regulation |
| TPS | Building environment technology |
| TSB | Technical equipment of buildings |
| TZS | Technological equipment of buildings |
| IOZI-Z | Officially authorised surveyor of the contractor |
| PLANNING DEPARTMENT | Spatial planning documentation |
| ÚR | Zoning decision |
| TUE | Central heating |
| VD | Production documentation |
| VN | High Voltage |
| VZT | Air handling equipment |
| ZBV | Change during construction |
| ZkP | Test operation |
| ZOV | Principles of construction organisation |
| ZS | Construction site equipment |
| ZSPD | Documentation of changes to the building before its completion |
| BTI | Health technical installations |
| HR | Application for approval |
| RU | Environment |

# Definition of

Contract for Work - EPC Contract SAKO and Contractor

Contract - Commissioning Agreement SAKO-BKOM

# Control of project risk management

The risk management plan will be checked in accordance with normal risk management practice and in particular with the tender documents Part III, Annex A 22 - Safety of performance. The Construction Manager's team, in collaboration with the Contractor's team and the Client, will proactively identify, analyse and assess other potential risks to verify that the risks are being properly managed by the Contractor. Recommendations will be made for each risk to reduce it to an acceptable level.

Identification of risks

The aim will be to find and identify hazards that may threaten the project and to try to record and describe these hazards as accurately as possible. In particular, the construction management team will focus on identifying significant hazards that may significantly affect the success of the project. The identification of hazards will be done in collaboration with the Client and the Contractor. The use of creative techniques such as brainstorming is expected. The identification of potential risks will also be supported by a construction risk inventory prepared by the HSE Coordinator.

The description of the risk will be made in appropriate detail, from its cause (source), through the scenario to the effect (impact) on the project itself. The output of the risk identification process will be a project risk register.

Risk analysis

It will be based on the preliminary methodology in Part III, Annex A 22 - Safety of Design, which will build on the risk register developed. Each risk will then be assigned a probability of occurrence and then a level of impact according to the values below.

Probability:

0		very low, close 0

1		very low and probably covered by insurance

2-3		low probability

4		medium probability (more likely not to occur)

5		medium probability (more likely to occur)

6		very likely

7		very likely, bordering on certainty (to be costed)

Impact:

C0	Negligible damage to health/negligible impact on the environment/negligible losses

C1	minimal injury without hospitalisation/minimal damage to the environment without permanent impact/damage to property or loss of production €5,000 - 50,000

C2	Injury requiring hospitalisation without permanent consequences/ serious damage to the environment without permanent consequences/ damage to property or loss of production €50 000 - 500 000

C3	serious injury with permanent consequences/ serious damage to the environment with potential for permanent damage requiring remediation/ damage to property or loss of production 500 000 - 5 000 000

C4	1-2 casualties/ significant damage to the environment with substantial scope for remediation/ damage to property or loss of production €5,000,000 - 50,000,000

C5	many casualties/ catastrophic damage to the environment with contamination of the surrounding environment and necessary evacuation/ property damage or loss of production over €50 000 000

The analysed risks will then be divided into regional categories:

- Financial

- Warranty and service

- Legislative

- Managerial/Project

- Procurement

- Business

- Technical

Each risk will then be assigned one of the following priority categories with a label:

- N	Unacceptable - must be treated

- O	Withdrawal - risk of withdrawal from the Work Contract (very high impact)

- P	Contractual penalties (failure to meet deadlines, parameters, etc.)

- VV	High impact risks at least C2

- xA	Acceptable risks - monitoring is sufficient

- x	Other risks - normal

Risk treatment and monitoring

On the basis of the selected risk category, an assessment of the risks shall be made and a treatment proposal shall be made taking into account the ALARP method, i.e. reducing the risk to as low a level as reasonably practicable. The aim of this phase is to reduce the overall value of all risks to a level that makes the project highly likely to be successfully implemented. In particular, the following treatment approaches will be applied, always according to the specification of the specific risk identified:

- Acceptance of risk

- Elimination of risk

- Transfer of risk

- Risk mitigation

Within the selected treatment type, each risk will be assigned a primary owner and a described risk management procedure and control frequency. The risk owner will then report to the designated senior members of the Client's project team and the Construction Manager any changes that have occurred, and the monitoring of the risks will be included as a regular item in the regular review day meetings between the Client and the Construction Manager.

Depending on the nature of the risk, a preventive procedure to avert the risk will also be added, possibly supplemented by a trigger signal, so that it is possible to identify in time that the risk is highly likely to materialise and a back-up plan to mitigate the impact can be implemented and there is room for the preparation of adequate measures.

The construction manager has identified and quantified the potential risks of the project, see Table 1.

Table1 - Qualitative and quantitative project risk analysis

| Risk | Cause | Consequence/possible damage | Risk level |
| --- | --- | --- | --- |
| No Work Contract will be signed | Demanding tender and qualification conditions, lack of interest in implementation | Project will not be implemented, costs incurred in the preparation of the Project | Malé - candidates registered in the current selection procedure |
| Failure to obtain a final building permit | Difficult permitting process, unenforceable DOSS conditions, parties to the proceedings | The project will not be implemented Preparation costs incurred (project preparation, site preparation, demolition) Restrictions on the operation of the site due to the commencement of works | Medium - construction with significant overlap outside the client's premises |
| Non-completion/interruption of construction | Unstable socio-economic situation, state of the construction market; non-performance by the contractor | Non-operation of the line, loss of costs already incurred, loss of revenue | Medium - inflation, epidemics |
| Possible non-receipt/reduction of subsidy | Non-compliance with subsidy conditions | Necessary co-financing of the project from other sources | Malé - conditions of the grant have not yet been submitted, the grant is being discussed |
| Failure to achieve the required quality of supply | Poor performance by the contractor, technological obstacles | Increased operation and maintenance costs | Malé - tender documentation prepared by a professional person - quality contractor (qualification requirements of the VZ) |
| Delays in construction due to the client's assumptions | Challenging conditions - construction during the client's operation, unknown conditions resulting from the building permit, epidemiological situation | Loss of revenue/higher implementation costs/non-compliance with subsidy conditions | High - cannot be predicted given the current global situation |
| Failure to achieve performance parameters | Line efficiency does not match input parameters | Loss of sales, failure to achieve planned profit | Malé - The technology is designed and delivered by the general contractor, tender documentation prepared by a professional person |
| Exceeding the estimated costs of the project | Incorrectly defined scope of construction in the tender documentation, incorrect cost estimate | Increased project implementation costs | Malé - Expert contracting authority |
| Construction accidents (accidents at work, damage to construction and equipment) | Work insubordination, unforeseen events | Loss of life, damage to health, damage to part of the building or technology, interruption of operations, delay in implementation | Low - Consistent HSE risk prevention throughout the Project |
| Interruption of the customer's operation | Accident at the construction site Failure to meet the contractor's schedule for coordinating shutdowns | Loss of sales, non-fulfilment of contractual obligations of the customer | Low - Coordination by SpSt, consistent prevention of OHS risks throughout the Project, coordination of tender documentation components |
| Failure to put the building into proper operation | Exceeding emission limits including noise, failure to obtain a positive opinion from DOSS. Change in standards/regulations | A wasted investment | Low - Quality tender documentation, valid planning permission and integrated permit, professional contractor |

Project risk allocation

O - Customer's risk

Z - contractor's risk

S - shared risk

- Errors in customer requirements						O

- Unpredictable physical conditions						O

- Archaeological and other findings on the construction site					S

- Contractor's documents								Z

- Rejection of technological equipment, materials and craftsmanship	Z

- Remedial work								Z

- Delays caused by the authorities							S

- Insufficient rate of progress of works						Z

- Unsuccessful entrance exams							Z

- Acceptance of part of the work								O

- Failure to remove the defect							Z

- Repeated testing								Z

- Late payment								O

- Failed exams after completion						Z

Risk prevention and management plan

Ways to reduce the impact of risks:

- Creation of time and financial reserves in the schedule and budget (the risks are borne by the contractor - but it has an impact on the client's costs)

- Selecting a reliable contractor - focus on the tendering process and evaluation of the contract

- Quality contract conditions

- Quality insurance for construction and installation risks

Prevention of selected risks

Table2 - Prevention of selected risks

| Risk | Degree of risk | Risk prevention |
| --- | --- | --- |
| Possible non-receipt/reduction of subsidy | Small | Consistent monitoring of the project progress and compliance with the grant conditions |
| Failure to achieve the required quality of supply | Small | Selection of supplier Verification of reference units Quality contractual conditions/penalties for non-compliance Consistent quality control |
| Delays in construction due to the client's assumptions | High | Selection of the contractor HMG with reserves Fines for failure to meet milestones |
| Failure to achieve performance parameters | Small | Choosing a quality contractor Emphasis on quality in implementation |
| Accidents on site | Low | Taking out quality insurance Checking compliance with safety rules during implementation |

# Specification of activities of individual members of the construction manager team

Team leader of the construction manager

Team Leader The Construction Manager is the responsible representative, manager and coordinator of the team. The Team Leader delegates his/her rights and responsibilities to his/her individual representatives. The Construction Manager Team Leader or another team member equipped with a Construction Manager Team Leader's credential shall be available at least every working day to perform the Construction Manager's activities. The responsibilities of the Construction Manager, and therefore the Construction Manager Team Leader, are primarily based on the Agreement and the Annexes thereto.

The following describes the main rights and responsibilities of the Construction Manager, but these are assigned to individual appointed members of the Construction Manager team depending the parameters of the work

- is responsible, ensures and controls all activities related to the project management of the project according to the Contract for Work;

- recommends the necessary instructions of the Client with respect to the Contractor within the framework of the concluded Contract for Work;

- Responsible for the activities of the Construction Manager's team in the area of project implementation control (payments, costs, tests, acceptance, samples, compliance with the Contract for Work, etc.);

- if necessary, participate in the interpretation of the documents constituting the Contract for Work;

- performs an ongoing check of the scope and validity of the required bank guarantees and insurance of the project contractor;

- Carry out continuous checking and confirmation of the financial amounts charged for the works carried out during the implementation of the project by the Contractor;

- keep records of the Contractor's energy consumption in connection with the connection to the Client's utilities (water; electricity, waste, etc.) during the implementation of the project;

- Exercises control by managing communication, reporting and organising meetings;

- exercise control over the change management and recommend the Client's proposals to the Contractor with regard to the implementation of the project and its compliance with the Contract for the Work;

- carries out quality control checks and recommends any proposals for rejecting partial performance or ensuring that discrepancies are rectified;

- checks the speed of the contractor's progress against the schedule and participates in its commenting and updating;

- Oversee the up-to-date risk register, which will include all risks identified by the Construction Manager's team and risks identified by the Contractor or the Client;

- coordinates the handover of the project according to the Contract for Work between the Client and the Contractor;

- assists the Client in relation to contractual correspondence with the Contractor and other entities externally.

During project implementation:

- familiarise themselves with the content of the contracts between the Client and the Contractor, in particular the Contractor's obligations, the conditions for the implementation of the project, etc., including payment terms and the payment schedule;

- Become familiar with applicable project permits and oversee project implementation in accordance with them;

- controls and approves the preparation of project documentation;

- is responsible for the proper operation and maintenance of equipment used in connection with the activities of his/her team;

- Responsible for checking the proper storage of materials and order on the construction site;

- monitors the development and progress of the project, as well as the quality of the work carried out;

- Responsible for carrying out the Contractor's inspection during the execution of the works;

- discusses, supervises and comments on the contractor's quality, inspection and testing plans;

- is responsible for the technical supervision and activities of the OSH coordinator during the project implementation;

- arranges and coordinates inspection days and takes minutes of these meetings

- convenes and manages emergency meetings of his team members;

- draws the Contractor's attention to the identified deficiencies in the works and deliveries, and requests that remedies be arranged;

- immediately inform the Client of any serious circumstances that occur during the execution of the works and deliveries;

- is responsible for the proper course of the change procedure, commissioning and assessment of the change from the point of view of the subject matter and price, in cooperation with the Client, cooperates in the approval of change sheets prepared by the contractor;

- controls the keeping of records of changes and the coordination/assurance of the transfer of changes to all participants in the project implementation;

- Responsible for checking all documents for the handover of the project by the Contractor

- controls and supervises the fulfilment of the requirements resulting from the approval and the removal of any defects in the approval;

- controls and supervises the elimination of defects and deficiencies detected at the handover and acceptance of the project;

- controls the clearing of the site equipment, including storage areas, their cleaning and acceptance;

- controls the restoration of the land and buildings around the construction site to their original state, and at the same time ensures proper photographic documentation during the execution of the work.

During the warranty/guarantee period

- provides technical support;

- checks that all claims of the client under the contractor's liability for defects, including liability for defects during the guarantee period and the issue of a certificate of removal, are duly satisfied;

- advises the client on the application of these claims so that the choice between these claims is optimal for the client;

- provide assistance and advice where necessary in the event of disputes over these claims.

Deputy Team Leader of the Construction Manager

The deputy is part of the team leadership, represents the team leader and exercises the rights and duties as delegated by the team leader.

Project Manager

The Project Manager is part of the Team Leadership and represents the Team Leader/Deputy Team Leader on site and exercises the rights and duties as delegated by the Team Leader. As directed by the Team Leader, the Construction Manager shall ensure, direct and coordinate the activities of the Team in the performance of the tasks under the Contract. He shall manage and control the Project from a project management perspective. Controls the management of project risks, monitors all risks associated with implementation and highlights important events for the Principal

Quality Management Coordinator

In the area of quality management system, it carries out mainly the following activities:

- become familiar with the Client's requirements regarding quality management in the project implementation;

- familiarisation with the complete documentation for the project implementation, in particular the project documentation prepared by the contractor and the conditions for the project implementation;

- familiarisation with all permits issued in relation to the project;

- controls the preparation of a quality plan by the Contractor in order to approve the quality management method in accordance with ČSN EN ISO 9001:2016 to be used in the performance of the Contract for the Work;

- controls the quality system in place during project implementation and monitors quality within the overall scope;

- coordinate and control all acceptance and testing of the Project in accordance with the Contract for Work;

- inspects all activities in terms of quality of material and workmanship;

- controls and records any non-conformities within its area of operation and agrees procedures for their resolution;

- monitors compliance with the project's inspection and testing plan;

- provides assistance in the handover and acceptance of the completed project, i.e. checking the handover and acceptance documents;

- controls all necessary tests, attestations and inspections according to the legal regulations in force at the time of execution and handover of the Project, which will demonstrate the achievement of the prescribed quality and prescribed technical parameters of the Project, including the acquisition of reports.

Documentation/Administration Coordinator

In the area of project documentation management, it mainly performs the following activities:

- become familiar with the Client's requirements, including the Client's administrative regulations;

- review and comment on the documentation management plan and the documentation handover plan proposed by the contractor for the implementation of the project;

- archive and maintain all correspondence, i.e. letters, emails, interim reports, minutes of meetings and communications, etc. within the framework of project implementation;

- checks and comments on the completeness of the project documentation submitted by the contractor during the project implementation and its marking;

- supervises the keeping of construction logs;

- Controls the marking of revisions and approval of design documents and other Contractor documents prepared by the Contractor, in particular, compiles and completes comments from other members of the Construction Manager's team into a comprehensive report;

- proper archiving of all project documentation as well as all other documentation created within the scope of the construction manager's activities or handed over by the contractor and the client;

- maintains proper archiving of copies of construction logs.

OSH Coordinator

The OSH Coordinator shall perform the following activities:

- mutual coordination of all construction participants leading to the elimination of potential risks arising from construction;

- Searching for risks in the work of all current contractors and ensuring that the contractors concerned are informed the potential impact of external risks on their activities;

- familiarization with the Client's requirements regarding OSH;

- ensuring all activities are carried out in accordance with the Legislation;

- Preparation and updating of OSH documentation for the Site (OSH Plan, OSH Plan update including annexes and overview of the Legal Regulations related to the construction);

- physical performance of the activities of the OSH coordinator during the construction on the construction site;

- checking the execution of individual works on the Construction Site from the point of view of OSH;

- notification of the identified deficiencies and proposal of corrective measures to the Customer;

- organising and actively participating in inspection days and coordination meetings on OSH;

- checking and ensuring any other requirements according to the Client's specifications based on the applicable legal regulations;

OSH coordinator during construction preparation:

- cooperates with the designer, the project documentation processor,

- prepares a written and graphic work safety plan with all necessary

and the necessary requirements and individual workflows for implementation,

- proposes appropriate OHS measures,

- prepare an overview of legal regulations related to the construction,

- prepare an overview of the risks that may occur during the implementation of the construction,

- prepare information on safety and health risks in the construction,

- develops suggestions and recommendations for technical solutions or organisational measures that are suitable for planning individual works in terms of ensuring a safe and health-safe working environment and working conditions,

- provide expert advice and recommendations on the requirements for ensuring safe and non-hazardous work, estimating the length of time required to carry out the planned work or activities, taking into account specific measures, working or technological procedures and  and the necessary organisation of the work during implementation,

- ensure that the plan, appropriate to the nature and extent of the construction and the local operating conditions of the site, contains the information, data and procedures drawn up in the detail necessary to ensure safe and non-hazardous work. It shall prepare a "Health and Safety Plan" and submit it to the Investor within 30 days after the conclusion of the Contract,

- is responsible for ensuring that the OHS plan is available on site at all times in one copy.

OSH coordinator during construction:

- coordinates the adoption of measures to ensure health and safety at work by individual contractors or persons authorised by them,

- gives suggestions and, at the request of the contractor, recommends technical solutions or measures to ensure occupational safety and health for the determination of working or technological procedures and planning of safe execution of works which, with regard to the material and temporal links in the implementation of the construction, will take place simultaneously or will be directly related to each other,

- co-operates in determining the time required for the safe performance of particular works or activities,

- monitors the execution of works on the construction site and verifies whether the requirements for occupational safety and health are observed and warns in writing of the specifically identified deficiencies and demands that corrective measures be taken without undue delay,

- controls the security of the site perimeter, including access and entry to the site to prevent unauthorised individuals from entering,

- cooperates with employee representatives for occupational safety and health 
and with the natural person carrying out the technical supervision of the builder,

- participates in the inspection of the construction to which he has been invited by the building authority

- in coordination with all contractors on the site, continuously update and adapt the plan and have the plan approved and signed by all contractors,

- proposes the dates of inspection days to ensure compliance with the plan with the participation of the contractors or persons authorised by them and organises their holding,

- monitors contractors' compliance with the plan and discusses with them the measures to be taken and the deadlines for correcting the identified deficiencies,

- records the identified deficiencies in occupational safety and health on the construction site, to which it has demonstrably drawn the contractor's attention, and records information on whether and how these deficiencies have been remedied.

- cooperates with the investor's representatives, with the employees' representatives for health and safety

- ensures the performance of other activities of the OSH coordinator in accordance with Act No. 309/2006 Coll., as amended, and Regulation No. 591/2006 Coll., as amended.

Surveyor

Supervises the progress of construction in terms of geodetic surveying. Cooperates with other construction participants, designers, ÚOZI-contractors in the matter of surveying requirements

- will hand over to the contractor, through ÚOZI-Z, the construction demarcation network. It ensures the control and remeasurement of the demarcation network during the construction;

- takes over and checks, exclusively from ÚOZI-Z, partial geodetic surveys and documentation of the actual execution of the construction;

- additionally, if necessary, performs control spatial measurements of the building;

- inspects the geometric plans of the completed construction and easements prior to the preparation of their clean copy;

Environmental Specialist

In particular, it has the following activities:

- prepare an environmental management plan

- continuously monitors the implementation and subsequent overall compliance with all requirements and conditions arising from the project permits (EIA; Zoning Decision, Project Permit, Integrated Permit; etc.) related to the environment;

- during the implementation of the construction, it carries out control mainly in the field of the environment, especially in the following aspects affecting the impact on the environment:

- noise during construction and commissioning,

- Transport to and from the site; including a transport plan to minimise impacts on local residents,

- emission load during commissioning,

- control of liquids so that they do not leak into the ground or into local watercourses,

- Control of dust, odours and fumes, including dust and mud polluting the roadway from site vehicles,

- waste management and disposal; this requires the correct categorisation of waste and its disposal to be properly secured and documented,

- Preparation and reclamation of the site after the completion of the project construction.

Economist

The control and management of project costs is the responsibility of the Construction Economist. The Construction Economist controls the execution of the financial schedule, the inventory of works and the tax documents (invoices) submitted by the contractor when individual milestones are reached. He is the assistant to the Project Management Group Leader, heeding the instructions of the Construction Manager and the Client. Maintains an archive of the Contractor's and Construction Manager's invoices, as per the SoD including any amendments. In the event that changes occur during construction (ZBV), monitors that their scope does not exceed the limit set by law or by the client.

It also carries out the following activities:

- records construction survey reports and construction invoices in paper and electronic form,

- controls the use of external sources of financing (subsidies) during the execution of the work, including control of the fulfilment of the conditions for the use of these sources,

- participates in the deliberations of the ZBV,

- cooperates in the preparation of change proposals (ZBV) and their approval (price negotiation of new items),

- performs other necessary work related to the financial aspect of the construction as directed by the Team Leader.

Technical consultancy and technical supervision

The activities of the technical advisory and technical supervision groups are mainly technical control and coordination in the preparation and implementation of the project. The focus of the team's activities is on the control and commenting on the project documentation, the control and coordination of works on the construction, acquisition, production and delivery (including quality and quality control), as well as supervision and cooperation in the commissioning of equipment, test operation and operation during the warranty period

The technical consulting team is divided into a construction group (TDS construction) and a technology group (TDS technology).

The designated member(s) of the technical advisory team must be on site at least every working day during the execution of the works. These team members shall be provided with a mandate to exercise the rights and duties of the Construction Manager for the inspection activity on site.

The technical supervision of the builder for the construction part (TDS) performs mainly the following activities:

  - become familiar with the client's requirements, especially those related to the construction part and the implementation of the project;

  - performs technical design control and supervision of all engineering and design activities, including the schedule of implementation of individual activities within its area of competence;

  - participates in the review and approval of project documentation prepared by the contractor in its area of competence;

  - ensures quality assurance control and compliance with the quality plan by the manufacturer as well as within the scope of the project implementation by the contractor in its area of competence;

  - carries out the control of the project implementation according to the construction area and carries out the performance of permanent construction supervision of the builder within the meaning of § 165 SZ;

  - control and supervise compliance with all building standards and technical regulations related to the Project;

  - controls the contractor in ensuring the removal and storage of demolished materials and construction debris in a landfill in accordance with the provisions of Act 541/2020 Coll., on waste, and the storage of soil in a landfill;

  - Inspects the performance of all necessary tests according to all related standards, including inspection of related test reports;

  - checks that the work is carried out in accordance with the project documentation and informs immediately of any non-compliance. In the event of discrepancies, it shall recommend procedures for resolving such discrepancies;

  - reports on the deficiencies found in the project implementation and makes entries in the construction logs;

  - participate in the acceptance of the site by the contractor before the start of the project or at its handover, including the execution of a protocol record;

  - inspect all works and supplies, with particular attention to works that will be covered or made inaccessible as the works progress;

The TDS construction group consists of members:

    - TDS Construction Group Leader

    - TDS civil engineering

    - TDS statics and dynamics of buildings

    - TDS Transport Construction

    - TDS electro power (building)

    - TDS MaR (building)

    - TDS Building Environment Technology

    - TDS Fire safety solution of the building

- TDS Technology (Technology Specialist)

The Technology Specialist (Boiler, Machinery, Process, Flue Gas Cleaning, Electrical + MaR, etc.) performs mainly the following activities:

  - familiarise themselves with the requirements of the client, in particular those relating to technology within their area of competence;

  - carries out technical design control of all engineering and project activities, including the schedule of implementation of individual activities within its area of competence;

  - participates in the review and approval of the project documentation and commissioning plan, performance tests, trial operation and warranty test prepared by the contractor in its area of competence;

  - ensures quality assurance control and compliance with the quality plan by the manufacturer as well as within the scope of the project implementation by the contractor in its area of competence;

  - control and supervise compliance with all relevant legislation in its field of competence from the design, manufacturing and assembly phases to commissioning and final handover;

  - controls the performance of all necessary tests according to the Contract for Work, including the preparation of related test reports;

  - reports on the deficiencies found in the project implementation and makes entries in the construction logs;

  - supervises the progress of the installation and commissioning of the Line and related auxiliary operations, if the work is carried out in accordance with the project documentation and immediately informs of any non-compliance. In the event of discrepancies, it shall recommend procedures to resolve such discrepancies;

  - participates in tests, from functional tests on the part of the equipment manufacturer to the commissioning of the line within its area of competence.

The TDS Technology Group consists of the following members:

    - TDS  Group Leader

    - Boiler and Accessories Specialist

    - Specialist for machine shop, rotating machinery incl. turbines

    - Welding Specialist / Quality

    - Process Technology Specialist

    - Specialist in HV, LV electrical engineering

    - MaR and technology management specialist ASŘTP

    - Flue gas cleaning specialist

    - Technology Specialist OK

    - Waste to Energy Specialist

# Project documentation management system

Control of project documentation management is primarily the responsibility of the project administration in cooperation with the Project Manager, The Construction Manager, in the context of control of documentation management, shall ensure, in cooperation with the Contractor, the efficient and effective maintenance and record keeping of the receipt, distribution/distribution and archiving of all technical and other project documentation. Further, he/she shall ensure that the distribution of documentation and archiving of all documents generated is consistent with the needs of the Project as per the scope of the Contract Work. The control of documentation in the project will be closely linked and coordinated with all stakeholders involved in the project.

The Construction Manager shall approve the Contractor's submittal of firm procedures for the preparation, distribution, circulation, and filing of documents necessary for the proper execution of the Work.

In cooperation with the Contractor, the Construction Manager shall ensure:

- preparation of the document registration procedure,

- Preparation of a register of documents to be delivered on a specific date in relation to the Contract for Work, identifying all documents to be delivered with expected start and completion dates and their current status to ensure accurate tracking and reporting of work in progress,

- the creation of a documentation centre, which includes:

- creation and maintenance of a documentation database,

- the document storage system and the requirements for transmitting documents;

It also controls the security in the framework of other activities of the documentation centre during the implementation of the project:

- Distribution of all line documentation issued by the Contractor, equipment subcontractors, inspection authorities or any third parties to ensure that the responsible personnel of the Employer and the Site Manager are aware of the latest status,

- effective tracking and control of all documents to be delivered,

- reporting on the progress of the work in relation to the actual state of the document,

- sending documentation according to the plan, actual and planned deadlines within the register of system-generated term documents,

- Document identification to ensure accurate monitoring and status reporting;

- completion of the final documentation of the line, which will be handed over by the Contractor to the Client before the Handover of the Work.

All valid documentation will be kept in the Czech language.

The construction manager will store the records in an appropriate manner in accordance with Act No. 499/2004 Coll., on archiving and file service and on amendments to certain acts, as amended, 
and in accordance with Act No 563/1991 Coll., on Accounting, as amended, for a period of ten years after the financial closure of the project, but at the same time for at least three years after the closure of the operational programme pursuant to Article 90 et seq. 1083/2006, all original accounting documents, the Contract for the Work, including any amendments thereto, and other original documents relating to the Contract for the Work, starting from 1 January of the following calendar year after the last payment for the project has been made.

Correspondence register

All correspondence during the project will be entered into a correspondence register. This register will contain at least the following information:

- Name of subject of correspondence

- Type of correspondence (e.g. contractual, technical, business)

- Form of correspondence (e.g. email, data box, post)

- Requirement for answer (yes/no)

- Date of dispatch including recipients

- Status (open/closed)

- Date of reply

Description of documentation management control

The control of documentation management by the Contractor will be carried out at two levels according to the type of documents submitted. The process will vary whether the document being submitted is listed in the "Revisable Design and Construction Data" annex or is a normal document required for Project implementation but does not require validation by the Client

Contract management regime

The Contractor shall forward the document to the Construction Manager's team via the notified contact address for sending project documentation. The Administration and Documentation Specialist will assess whether the document is formally eligible for further work for the Construction Manager team. Documents will be stored in the designated document management software/application. Responsible parties as per the document matrix will have a 20-day review and comment period. The document with comments and with the Construction Manager's review report will be sent by the Project Documentation Specialist to the Client. The Client will review the document and forward the document to the Construction Manager/Contractor within the contractual period for incorporation of comments and forwarding to the Contractor.

See. Annex No. 1 to this Annex No. 2 of the Commissioning Agreement.

Current management mode

The Contractor shall forward the document to the Construction Manager's team via the notified contact address for sending project documentation. The Administration and Documentation Specialist will assess whether the document is formally eligible for further work for the Construction Manager team. Documents will be stored in the designated document management software/application. Responsible parties as per the document matrix will have a 14-day review and comment period. If approved by the relevant specialists, the document will be electronically agreed and can be submitted for sign off. In the event of comments from the Construction Manager, the document will be referred back to the Contractor for incorporation. After checking whether the incorporation has been carried out, the document will be electronically approved, signed and submitted to the client. The document will then be marked as approved and placed in the archive.

See. Annex No. 2 of this Annex No. 2 of the Commissioning Agreement.

# Project Scope Control

The Construction Manager shall inspect the work performed by the Contractor and its subcontractors to complete the Project in accordance with the executed Contract for Work in terms of meeting the Contract requirements and the overall requirements of the Client. To this end, the Construction Manager shall provide the activities necessary to monitor that all engineering and design services, as well as fabrication, installation, acceptance, testing, delivery, construction, commissioning and testing of the minimum guaranteed parameters under the Contract Work, including the warranty period, are performed in accordance with the Contract Work.

The process of project scope review by the construction manager is structured as follows:

- Inspection during construction

- During construction, the Construction Manager shall verify that the Work is being performed in accordance with the schedule and according to the technical requirements defined in the Contract for Work. In addition, the Construction Manager shall also monitor deficiencies in the organisation, staffing, health and safety, quality assurance, project and construction management, and the Contractor's construction, material delivery, commissioning and testing procedures. As a result, it shall closely monitor the progress of the works and report regularly to the Employer's Project Manager. This process is formalised by reporting inspection days with the client and issuing interim reports on the project implementation. The Project Manager also simultaneously reviews and comments on the weekly/monthly progress reports from the Contractor.

- Commissioning control

- The site manager will oversee the complete commissioning of the line. Specifically, he/she shall check the start-up procedures, acceptance test manuals, verification plan for minimum guaranteed operating parameters, etc., which must be assessed well in advance of the actual commissioning. The site manager shall also check that the client's personnel have been trained to the required standards and procedures by the contractor and that all safe systems of work and other operating procedures have been applied.

- Control of guaranteed parameters

- The Construction Manager controls the results of the individual tests and technical requirements set out in the Contract for the Work. Upon completion of the tests and testing of the minimum operational and guaranteed parameters, the Construction Manager shall review and comment on the Contractor's reports on the tests and tests carried out and report accordingly to the Client. The Construction Manager shall ensure that the requirements in the Contract Work are followed during the Handover of the Work. The Construction Manager shall, in cooperation with the Contractor, prepare appropriate forms for the Certificate of Completion and Handover of the Work and establish a list of documents to be attached thereto. Reports of the results of the tests and trials carried out shall be issued on completion of the inspections and tests. All findings and any comments shall be recorded in a summary report. Upon completion of the Work, the Construction Manager's team shall prepare a final report on the final completion of the Work in accordance with the terms of the Work Contract.

It is elaborated in more detail in the individual chapters of the project strategy. These are in particular Chapter 16 (Construction and Delivery Control) and Chapter 17 (Commissioning Process).

Table3 - Dates of documentation checks and reports to be submitted

| Check | Construction manager | Customer | Note |
| --- | --- | --- | --- |
| Project documentation | 21 days | 7 days | (Article 11.5 of the Contract for Work) Within 21 days, the construction manager submits an inspection report to the Client, the Client submits comments to the Contractor within 28 days for their incorporation |
| Check of implementation and compliance with documentation | 7 days |  | The construction manager checks the compliance of the implementation with the documentation continuously, and the detected facts are forwarded to the Client within 7 days of their discovery. |
| Amendment procedures / opposition to proposals | 7 days |  | (Article 27 of the Work Contract) Within 7 days, the Construction Manager shall provide the Client with an opinion on the proposed change to the Contract obligation. |
| Statement on the inspection of the construction diary | 1 per week |  | (Article 14.26 of the Contract for Work) The construction manager shall confirm the inspection of the construction log at least once a week with his signature and attach his opinion to the entries. |
| Minutes of meetings/arrangements/check-up days/workshops | 2 days |  | (Article 14.15 of the Contract for Work) The Construction Manager shall provide the Client with an opinion within 2 days of the affected meeting or inspection day. |
| Handover procedure | according to the terms in the SoD |  |  |
| Control of securing a building permit | 7 days |  | (Article 11.12 of the Contract for Work) The Construction Manager shall provide the Client within 7 days with an opinion on the Engineering outputs submitted by the Contractor. |
| Compliance check with the Legislation | 7 days |  | (Article 12.8 of the Contract for Work) The Construction Manager shall check the compliance of the implementation with the Legal Regulations on an ongoing basis, any detected . |
| Contractor's monthly report on the progress of the work |  |  | As part of the interim reports, the Construction Manager provides the Client with an opinion on the monthly reports prepared by the Contractor during the period. |
| Annual progress report | 14 days |  | on the first day of the following year |
| Final report | 35 days |  | from the signing of the protocol of Handover of the Work |
| Invoices | 7 days |  | (Article 26.7 of the Contract for Work) The Construction Manager is obliged to comment on the invoice-tax document (in particular with regard to its legitimacy, correctness and content) 7 days of its receipt from the Contractor. |
| Obligation under the Work Contract | 5 days before the deadline |  | The Construction Manager shall check the Contractor's performance of the obligations under the Contract for Work on an ongoing basis, informing the Contractor 5 days before the deadline whether the obligation has already been fulfilled or whether it has yet to be fulfilled. |

# Time control in the project

The time management requirements in the Work project are defined mainly by the Contract Schedule, the Work Contract and the Client's requirements.

As part of the project time control, which will be ongoing throughout the project, the Construction Manager will perform the following activities:

- Preparation of a control procedure for checking scheduling/harmonograms,

- Continuous control of all schedules during project implementation,

- ongoing identification of possible discrepancies in project planning by the contractor

The time control services to be performed by the Construction Manager on the Project shall be related to the approved schedule and the Contractor's progress schedules for the Project in accordance with the Contract Work. MS Project scheduling software will be used for scheduling.

Schedules and their milestones submitted by the Contractor for review by the Construction Manager:

- Detailed schedule:

- First delivery before signing of the Contract for Work, further updated in interim reports

- Six-week HMG for construction and installation:

- Submit the proposal for approval six months prior to installation of the machinery

- First delivery three months prior to installation of the machinery and then weekly document submissions at the appropriate stage of the

- Six-week HMG for commissioning:

- Submit the proposal for approval six months prior to installation of the machinery

- First delivery three months prior to commissioning and then weekly document submissions at the appropriate stage of the Project

The schedules will be checked against the planned and actual progress of the works, the status of approved materials and delivery of materials on site.

Due to the complexity of the project, the Contractor shall prepare and the Construction Manager shall review a "Project Progress Schedule" in addition to these schedules. It will be based on tracking key milestones that will be monitored at the Project Manager level. This Schedule will be monitored and evaluated at regular intervals (30 days) as part of the contract inspection days.

Other sub-schedules will be monitored at the individual TDS Specialist or Technology Specialist level as appropriate

# Cost Control in the Project

Coordination and collection of the Project cost control results is the responsibility of the Project Economist. The individual members of the Construction Manager's implementation team shall control, according to the allocation of activities within the Project, the eligibility of costs reported by the Contractor under the Contract for Work.

# Quality Control

The Quality Management System and Quality Control Coordination Specialist shall ensure that the Contractor has a quality management system in place throughout the execution of the work in accordance with the relevant standards. He checks and comments on the submitted quality plan and test plan according to the requirements defined in the client's requirements. The quality plan shall describe the method used to prepare, maintain and update the quality management system appropriate to the execution of the work. This document shall be updated whenever a fact arises that makes it necessary to change the quality plan/test plan. The deadline for submitting the quality manual for approval is within four weeks after the signature of the Contract.

The Construction Manager shall also manage and control the Contractor's submitted "Quality Control Plan", which shall be in accordance with ISO 10005.

To ensure proper quality of the work, the Quality Control Management and Coordination Specialist requires the following:

Control days

- The quality of the work will be dealt with in the normal course within the KD.

- The Quality Control Management and Coordination Specialist will attend the QA on a regular basis.

- The contractor will prepare a work plan for the following period according to the client's request. The plan shall be sent electronically to the relevant persons of the construction manager's team, including the quality control management and coordination specialist. The plan shall also include a schedule of inspections and tests for the next period.

Quality control days

- Separate quality control days will be called according to actual needs.

- The contractor shall submit a proposal for a solution to the failing tests without being asked.

Control and Test Plan (CTP)

- The CPCs will be prepared on forms to be approved by the Construction Manager and the Client

- The KPPs shall be submitted for review by the Contractor in sufficient time to allow for their approval prior to commencement of work.

- The CPCs will be divided according to the construction objects (SO) and operational sets (PS) and will be given a serial number.

- They will be submitted to the Construction Manager, the Quality Control Management and Coordination Specialist, and the appropriate TDS for approval.

- During the approval of the CPP, the contractor shall ensure communication between the approvers and the CPP preparers.

- The entities responsible for approving the CPP will certify the approval by a dated signature on the cover sheet.

- Approved CUPs will be deposited as directed by the Construction Manager.

- The way of working with the QPDs, keeping them electronically or in paper form, signing and storing them will be further regulated in the quality plan

Materials and products

- All materials and products used in the construction will be listed in the material books.

- The material books are prepared by the contractor.

- The breakdown of the material books will be according to the customer's requirements.

- Material books will contain an exhaustive summary of materials and products, although their approval may be phased.

- The marking of the books will be in capital letters, the marking of the material in numerals (A 1).

- When submitting materials and products for approval, the contractor shall base his submission on the approved project documentation.

- The materials will be approved by the relevant TDS.

- The material books will indicate the designation of the SO and PS in which they will be used, the date of submission of the supporting documents for the respective material and product (Declaration, Certificate, etc.), and the dates and signatures of the approvers.

- The material books will be continuously supplemented and updated.

- The original material books shall be stored at a location designated by the Construction Manager in paper or electronic form.

- Submission of materials and products for approval must occur in a timely manner so that materials and products are always approved prior to installation.

- Unapproved materials and products cannot be incorporated,

- Materials and products in special treatment, recipes of mixtures, etc. will be documented in the required manner.

- All documents will be up-to-date, complete and in the Czech language

- For products that are proven in the summaries, those that will be specifically used on site will be indicated.

- The document files for approved materials and products will be in bundles numbered identically to the serial number of the material and product in the material book.

- Inspection of the use of approved materials and products is carried out by the relevant TDS, which will request delivery notes for inspection if necessary.

Technological regulations (TP)

- The TPs will be summarized in the TP list.

- They will be developed in a comprehensive scope covering all construction and installation works and activities.

- The TPs will be identified by serial numbers in consecutive numerical order with the CPP.

- They will be submitted for approval to the Construction Manager represented by the Quality Control Management and Coordination Specialist , the appropriate TDS and the OHS Coordinator.

- The cover sheet will include the dates and signatures of the approvers.

- For concrete and asphalt mixtures, the TPs will also include transport times.

Inspection and test book

- The Contractor shall keep the inspection and test book.

- The construction manager shall continuously check the maintenance of the inspection and test book

- Tests will be dated to correspond to the test records in the Construction Log (CL) and will have serial numbers.

- The evaluation of the tests (V/N) will be indicated in the inspection and test book.

- The inspection and test book will be kept up to date.

- The inspection and test book will be kept electronically and will be permanently accessible to the client and the construction manager.

Test

- A record of each of the tests will be given.

- The record shall include details of the type of test, the equipment used, its calibration, etc.

- The test report shall be made by the person conducting the test.

- The test reports shall be filed in the inspection and test book immediately after the test has been evaluated.

- The contractor shall ensure that the protocol is clearly marked by the protocol preparer with the SO and PS number, the KZP and the serial number of the test according to the KZP.

In general, the tests will be carried out from the time of commencement of the construction work up to the performance tests. Quality tests will be carried out on site and with the equipment suppliers. The Contractor shall provide an Inspection and Testing Plan (ITP) for each unit, which shall be reviewed and commented on by the Construction Manager. After incorporation of the comments, the Controller shall approve the inspection and testing plan, defining his participation in each inspection and test. The inspection and test plan can then be submitted for signature. Everything must follow the submitted project document management process.

- Quality tests on site

These tests will be used by the construction manager to verify the quality and execution of the work, both the construction part and the technology

- Inspection of suppliers

For complex technologies, the construction manager will inspect the manufacturing plants together with the client before the individual components are delivered to the site

- Function tests

They will consist of individual and comprehensive examinations.

Plan of works

The work plan will be divided into SO and PS.

# Checking that the environmental requirements of the project are met

The Environmental Specialist is responsible for checking that the environmental requirements of the project are met.

Prior to the signing of the Contract for Work, a template of the Environmental Construction Plan document will be submitted by the Contractor through the Construction Manager. Upon approval of the template, the Environmental Construction Plan will be prepared and submitted 1 month after the signing of the Contract for Work and updated and reviewed by the Construction Manager at regular monthly intervals.

The Construction Manager shall review the environmental construction plan submitted by the Contractor. The plan shall discuss all relevant environmental risk activities and shall include, as a minimum:

- noise during construction and commissioning,

- Transport to and from the site; including a transport plan to minimise impacts on local residents,

- emission load during commissioning,

- control of liquids so that they do not leak into the ground or into local watercourses,

- Control of dust, odours and fumes, including dust and mud polluting the roadway from site vehicles,

- waste management and disposal; this requires the correct categorisation of waste and disposal to be properly secured and documented,

- Preparation and reclamation of the site after the completion of the project construction.

The process of preparing an environmental plan for the development:

- the contractor shall submit a summary of all activities or construction processes that will take place on the site,

- the contractor, in cooperation with the client and the inspection, will identify the environmental aspects and carry out their assessment resulting in the Environmental Aspects Register,

- on significant aspects or on all aspects, if required by the client, procedures and criteria for their monitoring will be established, i.e. a schedule of inspections and evaluation,

- All mandatory conditions based on the issued permits of the state administration will be incorporated into this schedule,

- The plan will also include a definition of responsibilities for individual activities and an overview of measures to reduce negative impacts on the environment,

- if new activities and new aspects are identified during construction, the plan will be reviewed and updated.

The input for the preparation of the plan will consist mainly of:

- integrated permit for the building permit for the Link

- potential hazards in the workplace and its related processes and operations identified in the OHS plan,

- the client's environmental policy,

- the relevant conditions in the permits,

- assessment of environmental risks that may arise during construction.

# Health and safety inspection in the project

Health and safety inspection in the project

OHS management will be an integral part of the project implementation and will be ensured during all phases of construction.

The construction manager will ensure the control of OSH management within the project implementation according to the requirements of Act No. 309/2006 Coll. Each employer is responsible for the control and management of OSH. The on-site H&S Coordinator shall be appointed by the Client and shall be provided by a member of the Construction Manager's team. The OHS Coordinator shall comply with all requirements under the relevant legislation. The primary responsibility of the HSE Coordinator will be to prepare an HSE Plan in accordance with the Legislation and then to monitor compliance with the Plan on an ongoing basis during the construction of the Project. The OHS Plan will respect the nature of the Project and the continuities in the provision of OHS under the Works Contract.

The OHS Coordinator shall ensure control of the health and safety plan for the project prepared by the Contractor, which sets out how the Contractor will oversee health and safety throughout the duration of the project, documents risk assessments and establishes procedures for all planned activities. These will include a wide range of standard tasks or tasks specific to a particular operation which present certain risks. They will address all relevant aspects of health and safety at work, from the care and training of employees to site management and hazardous materials.

In addition, the OHS Coordinator must ensure that all contractors working on the site collect information on accidents, injuries and other dangerous occurrences and report them regularly. He must also require them to actively promote workplace safety through specific safety compliance guidelines. The implementation team shall intensively monitor safety deficiencies during its presence on site and, if it detects them, require immediate action to correct them.

The Construction Manager's OHS Coordinator and the Contractor's OHS Technician will jointly organize inspection days conducted to review the Contractor's designs from a health and  perspective. The Contractor shall attend these inspection days and ensure the presence of suitably qualified persons to explain and discuss the Contractor's approach to meeting the requirements of the OHS Regulations and any other requirements arising from the design, including but not limited to the design for the manufacture of components forming part of the Works.

The Contractor shall provide such supporting information as the Construction Manager may require to prepare for and participate in these inspection days. The Contractor shall confirm and record its activities and actions to meet the requirement of the outcomes of the OHS inspection days.

# Project documentation control

The Construction Manager shall control the Contractor's preparation of the overall Project design from the time of commencement through to commissioning and final acceptance of the Project to ensure that the provisions in the Contract for Work are met. The Project includes a significant amount of design work and therefore a basic assessment of the design documents and identification of potential deficiencies and issues in relation to meeting the terms of the Contract for Work is required. The subject of the Project inspection is its completeness and compliance with the terms of the Contract for Work and applicable legislation. Responsibility for the accuracy and completeness of the Project documentation remains with the Contractor.

The construction manager controls in particular the preparation of the design, ongoing construction, assembly work and commissioning of the line by the contractor in accordance with the Contract for Work. The primary duty of the Technical Advisor is to check that the work is being carried out in accordance with the schedule and according to the technical requirements defined in the Contract for Work. In addition, the Construction Manager shall also monitor deficiencies in the organization, staffing, health and safety, quality assurance, project and construction management, and the Contractor's construction, material delivery, commissioning, and testing procedures for the Project. As a result, it shall closely monitor the progress of the works and report regularly to the Client's Project Manager. This process shall be formalised by weekly reporting on inspection days and by issuing interim reports on the implementation of the Project. The Project Manager shall review and seek the views of the Contractor on the weekly/monthly progress reports on the progress of the Works.

The Construction Manager shall participate in the inspection for the complete commissioning of the Line. Specifically, he/she shall check the commissioning procedures, acceptance test manuals, verification plan for minimum guaranteed operating parameters, etc., which shall be assessed well in advance of the actual commissioning. It shall also check that the client's personnel have been trained to the required standards and procedures by the contractor and that all safe systems of work and other operating procedures have been applied.

The Construction Manager controls the results of the individual tests and technical requirements set out in the Contract for the Work. Upon completion of the tests and testing of the minimum operating and guaranteed parameters, the Employer shall review and comment on the Contractor's reports on the tests and trials carried out and report to the Employer accordingly. The Construction Manager shall, in cooperation with the Contractor, prepare appropriate forms for the Certificate of Completion and Handover of the Project and establish a list of documents to be attached thereto. Reports of the results of the tests and trials carried out shall be issued after completion of the inspections and tests. All findings and any comments shall be recorded in a summary report. Upon completion of the Work, the Contractor shall prepare a Final Completion Report for the Project in accordance with the terms of the Contract for Work.

The construction manager must also assess any substandard conditions during the warranty period and develop a corrective action plan at the request of the client. In addition, the Construction Manager shall, if requested by the Client, recommend a schedule for correcting defects in the Project. The Client shall comment on the Contractor's communication prepared by the Contractor pursuant to Paragraph 19.1 of the Contract for Work. In addition to the communication pursuant to the preceding sentence, the Construction Manager shall indicate whether the Contractor's proposals raised in the framework correspond to the actual state of affairs and provide such other information as may be necessary to enable the Construction Manager to assess the Contractor's communication.

The Construction Manager shall actively support the Employer's interests in identifying potential deficiencies in the Project and shall alert the Employer to such potential deficiencies that could lead to potential change claims by the Contractor throughout the duration of the Contract for Work.

The term Project Documentation means any drawings, reports, formulas, calculations, software and other documents and data relating to the design, construction, completion and operation of the Line from a civil engineering and technical point of view, which are one of the results of the Contractor's activities under the Contract for the Work. By design documentation is meant in particular all revisable design data, all stages of documentation according to Decree No. 131/2024, basic design and detail design.

Project documentation for the building permit (DPS) according to Decree 131/2024 Coll., as amended, will be prepared as a separate documentation and serves to obtain the permit for the project. This documentation will be prepared in  with Annex 4 to Decree 131/2024 Coll., as amended, and will be submitted for inspection to the construction manager or the client in accordance with the SoD. The DSP will be based mainly on packages LD1, CD1.

The contractor submits the project documentation according to the SoD for inspection. The Contract for Work defines the breakdown of the project documentation, the content and scope of the individual parts of the project documentation

The project documentation is divided into the following categories:

- Revisable design data - Layout (LD)

- Revisable Structural Data - Buildings and Building Section (CD)

- Revisable Design Data - Machinery (MD)

- Revisable Design Data - Electrical Equipment (ED)

- Revisable design data - Automation (AD)

Design and Construction data are submitted in "packages" during the Project that correspond to the Project implementation phase:

- Disposition (LD)			LD1-LD5 packages

- Buildings and construction part (CD)	Packages CD1-CD5

- Machinery (MD)		 packages

- Electrical Equipment (ED)		ED1-ED3 packages

- Automation (AD)			Packages AD1-AD3

For each new documentation package, it is essential to check three factors:

- Compliance of the documentation with the Building Act, i.e. in particular compliance with the conditions of the zoning decision and integrated permit and compliance with other conditions arising from the Building Act and related regulations.

- Consistency of the documentation with previously issued revisable design and construction data

- Consistency of the revisable data with the documentation for the building permit, including incorporation of any changes and additional requirements resulting from the construction procedure. If new facts or requirements emerge, it is necessary to ensure that they are reflected in all ongoing and subsequent stages of the project documentation

Control of the project documentation will be carried out on an ongoing basis (supervision of work in progress). During design process, the progress of the design work and the technical design of the project will be discussed at Production Committees convened by the Construction Manager and/or during regular construction inspection days.

The stages of the documentation according to the SoD will be submitted for overall control. As part of the construction documentation management, it will be ensured that the documentation, or the relevant part thereof, has been demonstrably submitted for review by all affected team members. The control will focus in particular on:

Checking the content, scope and details of the project documentation

The content, scope (completeness) and detail of the project documentation will be checked in relation to the SoD (e.g. Annex C1) and in relation to legal regulations and standards (e.g. Decree 1331/2024 Coll. as amended).

Checking compliance with legislative requirements

The documentation specialist will ensure, in cooperation with the team's technical specialists, that the legislative requirements and the requirements of the decisions and opinions already issued for the construction are checked. At the same time, the possible further development of the construction permitting in relation to the issued documentation and the possible impact on the commissioning, trial operation and approval of the construction will be assessed.

Check for technical correctness

The technical content of the documentation will be checked by Team specialists with the appropriate expertise.

During the documentation review, the project manager convenes meetings to discuss the coordination of individual parts of the PD, the interim and final findings of individual specialists and the implications of specific findings for other parts. A report is issued on the findings of the review. The report will include, inter alia, comments on the technical design and highlighting specific deficiencies

In more detail, the main activities of the construction manager's team in the preparation of the project documentation (processing of design and construction data) and preparation for construction are described below according to the important nodal points of the Project.

Main activities of the construction manager in the framework of basic design (MD1, AD1, ED1, CD1, LD1) and planning permission

- Control of the Contractor's compliance with the requirements set out in the Contract for the Work in the structural and technical design of the Project;

- Control of the project submittal schedule and any other documents defined in the Contract for the Work that the Contractor must submit to the Construction Manager and that are subject to review during the performance of the Work;

- Basic assessment of all documents related to the basic design concepts of the technological and construction solution of the Project;

- Assessment of key system concepts and design of key technology and construction parts of the Project for completeness and compliance with the SoD requirements;

- Assessment of basic drawings such as electrical wiring diagrams, control system philosophy, balance of plant and process flow diagrams, key process and instrumentation diagrams and layout/construction drawings of the Project for completeness and compliance with SOD requirements;

- Assessment of the proposal with regard to compliance with all requirements arising from the Project permits (EIA; Zoning Decision; Integrated Permit; etc.);

- Assessment, review and approval of the project documentation for the issuance of the Project Permit, including, where applicable, the project documentation for the amendment of the zoning decision. whether the documentation complies with the applicable legislation and the requirements of the SoD in terms of content and scope.

Main activities of the construction manager within the detail design (especially MD2, AD2, ED2 and the elaboration of LD and CD corresponding to PDPS)

- Control of the Contractor's compliance with the requirements set out in the Contract for the Work in the final structural and technical design of the Project (compliance with technical parameters and agreements on permissible deviations and technical clarifications);

- Control of the project documentation handover schedule and all other documents defined in the Contract for the Work;

- Basic assessment of the main operational, technical and construction facilities including the philosophy of system redundancy of the Project, in particular the assessment whether the requirements of the SoD are met;

- Assessment of the compliance of the standards proposed by the Contractor for the Project with legal regulations

- Assessment of the situation plan with regard to the movement of vehicles, equipment, heavy and light loading/unloading cranes and hoists etc.;

- Assessment of the electrical system plan and redundancy with particular emphasis on ensuring that a failure at one location does not cause the Line to shut down or shut down the Customer's existing equipment, in particular assessing whether the requirements of the SoD are met;

- In cooperation with the Customer, assessment of the integration of the Line into the entire system of the Customer's existing facility in terms of layout and situational design, technological interconnection, mechanical design and design of the electrical installation and control system including measurement and control;

- Assessment of essential process and equipment schematics, single-pole schematics, wiring and instrumentation and control schematics, safety schematics, logic schematics, etc., in particular assessment of whether SoD requirements are met;

- Assessment of the operation and maintenance manual for the equipment supplied under the Project by the EPC Contractor. Assessment of the overall design and structure of the manuals;

- Basic assessment of the main calculations and design dimensioning of the main equipment and structures of the Project

- Checking compliance of the protection study and safety relay setting calculations with the SoD. Contractor's assessment of overall Project security functionality;

- Review all quality control procedures and other design procedures proposed by the Contractor to determine if all design requirements have been fully implemented in accordance with the Contract Work;

- Assess the adequacy of information in the Contractor's engineering geology and geotechnical investigation and laboratory sample testing procedures. In addition, an assessment of the Contractor's interpretation of surveys, studies, and laboratory results for the purpose of monitoring whether the design of the construction portion of the Project, such as foundations, supporting structures, etc., is based on reliable and adequate data;

- Assess the completeness of the basic and detailed design information for the civil, mechanical and electrical work to monitor overall compliance with the Project intent;

- Assessment of design criteria/procedures to protect Project structures from degradation by surrounding local influences;

- Review of quality control procedures and associated acceptance plans to monitor that the Contractor is controlling products and material deliveries to the required levels in accordance with the specifications and agreed standards under the Contract for the Work

- Assessment of the adequacy and suitability of the documentation prepared for training of the Principal's staff

- Assessment of any specialised studies prepared by the contractor (HAZOP, SIL, etc.).

# Control of construction and delivery

The Technical Consultancy and Supervision Team (TDS) provides constant supervision of the progress of work on site. Continuous monitoring is carried out with the involvement of the relevant specialists according to the current progress of the work. The control includes compliance of the work progress with the construction schedule. The involvement of the individual specialists in the continuous monitoring is planned in relation to the schedule.

Technical inspection days shall be convened to check the progress of construction and delivery. These inspection days shall be attended by a wider range of affected specialists from the Construction Manager and the Contractor. In particular, the conclusions of the interim construction inspections are discussed at the production committees and the activities of all construction participants are coordinated.

Regular inspection days shall be organised by the Contractor in accordance with the Contract for the Work. In addition to the regular inspection days, an extraordinary inspection day may be convened by the Contractor or the Client as required.

The construction manager shall keep the client informed of the progress of construction, inspections carried out and other important facts in relation to the project, and shall submit a  report on request.

The inspection activity is carried out in parallel with the author's supervision of the designer.

The subject of the aforementioned inspections is in particular the compliance of works and deliveries with the current approved project documentation (construction data) and the construction schedule, compliance with technological procedures and the performance of continuous tests, acceptance and inspections. Compliance with the relevant regulations in relation to construction and delivery will also be checked

Demolition works, demolition

Prior to the commencement of demolition works, the contractor shall carry out a construction-technical survey, prepare a technological procedure, a waste management plan and ensure the disconnection of the demolished buildings and parts from the utilities. The above activities will be checked and the outputs will be approved. The compliance of the procedures and activities with the submitted documentation will be verified during the interim inspection. Close liaison with the site H&S coordinator and the H&S engineers concerned is an integral part of the inspection.

Construction work

Construction work on site will be carried out in accordance with the approved project documentation. For each activity, the contractor shall submit in advance (at least eight days) a Technological Procedure with a risk assessment. These documents shall be approved by the Construction Manager prior to the commencement of works.

The inspection of construction work is focused on several areas:

- Compliance with technological procedures, including conditions for work and installation

- Compliance with project documentation in cooperation with AD

- Compliance of the work progress with the schedule, especially in relation to the technical continuity of the work.

- Control of the materials used, including their storage and processing

- Inspection and acceptance of covered parts, structures and process steps

- Control of OSH compliance in cooperation with the coordinator

Supplies

Products, structural units and complete technological and operational sets are delivered to the site. Production is usually carried out off-site. The production and assembly of individual units and components are checked in accordance with the approved Quality Plan. All units and assemblies are manufactured on the basis of approved production documentation.

On site, the compliance of the delivery with the approved documentation is verified. Subsequently, the method of storage and handling on site and the installation procedures are checked.

Control of coordination of construction works and deliveries

The contractor is responsible for the coordination of activities on the construction site and prepares the schedule of works and updates it continuously. The schedule itself is the subject of control, where the technical continuity of the works and deliveries must be verified, and its observance. The aim of the check is to highlight possible problems with the continuity of individual works and deliveries due to, for example, insufficient construction readiness or spatial conflicts.

The main tasks of the technical consultancy and technical supervision team during construction, production and installation are listed in detail below:

- Assessing the Contractor's individual procedures and activities to check compliance with legal regulations and requirements under the Contract for Work during the course of the project.

- Providing assistance in securing all necessary surveys by the Contractor required for the handover of the site and subsequently for the proper execution and completion of the project.

- Handover of the project site to the Contractor in accordance with the Contract for the Work, in particular by coordinating with the Contractor and subsequently controlling:

- Surface roads within the area affected by project construction with possible connections to service existing facilities.

- Reporting system for the movement of larger and extreme construction equipment, including the determination of the mode of movement of this equipment in the SAKO area.

- Placement of machinery, materials and other equipment on the SAKO premises.

- Familiarization with all affected utilities within the SAKO site and the process piping of existing equipment affected by the project.

- Checking connection points and project delivery boundaries, etc.

- Providing assistance in negotiating and arranging for any special use of roads and public areas, including the Contractor's supervision of the provision of traffic signs for traffic restrictions, their maintenance and relocation and subsequent removal.

- Performance of technical supervision on the construction site throughout the project implementation in accordance with legal regulations.

- Review the delivery activities and procedures of the Contractor and its subcontractors to verify that the delivery schedule is consistent with the project schedule.

- Inspection of the course of equipment acceptance at the Contractor's or its Subcontractors' premises relating to key parts of the project (if mandatory participation in such inspection is required under the Contract for Work). Compliance with the terms of the Work Contract during the acceptance of key portions of the Work shall be witnessed by qualified personnel of the Principal, i.e. an authorized member of the Implementation Team. The Principal shall receive a formal acceptance report from each site visit including documentation of testing. The following acceptance of key equipment shall be part of the basic services provided, but always at the direction of the Principal:

- Boiler system

- Engine Room

- Electro part

- Lifting equipment

- Gas pipelines

- Coordination of the progress of the acceptance of parts of the project by independent agencies (where required under the Contract for Work) as well as review of the submitted acceptance reports. Compliance with the terms of the Works Contract in the context of the acceptance of key components shall be witnessed by the Principal's qualified staff, i.e. an authorised member of the implementation team. The Principal shall receive a formal acceptance report from each site visit including documentation of testing

- Carrying out acceptance inspections and checking their results during the construction, installation and commissioning of the project and including checking the Contractor's compliance with the project procedures at the construction site to the extent of at least:

- Inspections during construction, material quality control, weld inspection and evaluation, welder certification, etc.,

- Material tests and inspections during assembly,

- Participation in building and pressure tests, checking results and confirming acceptance, etc.;

- Inspection of acceptance of key equipment by the Contractor on site, in particular that the Contractor:

- Checked that the equipment conforms to standards and specifications.

- He properly identified and logged the device.

- He stored and preserved the equipment properly, etc.;

- Quality control of materials used by the Contractor in the execution of the project;

- Review of overall construction activity in relation to the construction schedule (movement and deployment of personnel), including identification of problems, deviations, non-compliance, delays during construction, and actions to be taken to maintain the schedule and quality of the project in accordance with the Contract for Work;

- Verification of compliance with all conditions required under the Contract Work for approval to commence and complete each phase of construction/installation/commissioning declared by the Contractor;

- Inspection and coordination of site clearance by the contractor, including the execution of a protocol record.

# Commissioning process

The main tasks of the technical advisory and technical supervision team during the commissioning process are listed in detail below:

- Inspection of Project connection points and delivery boundaries in connection with existing utilities and process piping, including any potential process connections between the new and Principal's existing facilities.

- Checking that the required records and documentation are prepared, distributed, commented on and completed for commissioning as required by the Contract for Work.

- Assessment of the proposed pre-commissioning, commissioning and testing procedures, with subsequent inspection during their implementation, to be followed by the Contractor, in particular:

  - Assessment of the design of the chemical cleaning process, inspection during the entire chemical cleaning process, inspection of the quality assessment of the internal surfaces of the sampled pipes from predetermined parts of the plant;

  - Assessment of the design of the steam blowers, checking the evaluation of the parameters and conditions of the technological procedure during individual blowers, checking the evaluation of the control plates and evaluation of the level of purity and compliance with the steam quality criteria according to the design of the steam blowers;

  - Visual inspection of the functional units and systems, including comparison with the Project Documents, to confirm that the installation is complete;

  - Checking of system tests prior to energisation (e.g. electrical circuit interconnection tests, insulation resistance, etc.);

  - Control of tests of functional units under;

  - Checking that the tanks are filled with fuel, lubricants, water or other necessary operating media;

  - Checking the start-up of individual devices and functional units of technological equipment and checking their correct operation;

  - Checking of air and flue gas piping and selected parameters of the boiler pressure system, checking the availability and stability of steam parameters (flow, pressure, temperature), checking of temperature fields of superheaters, checking that the maximum permissible temperature is not exceeded;

  - Checking the correct calibration of test measuring instruments, especially those used in operating parameter testing and performance testing;

  - Checking the hydraulic resistance of individual parts and comparing with design values;

  - Control of flue gas composition analysis;

  - Control of the chemical regime of the steam cycle, quality control of the produced treated demineralized water;

  - Checking the dynamic and control characteristics of individual devices, their interaction and limitations resulting from the device layout;

  - Checking the testing of permissible limit operating conditions and trends, the characteristics and behaviour of the equipment in these conditions and trends;

  - Noise and vibration control of selected equipment, etc;

- Review of the Contractor's proposed Performance and Warranty Testing Program and check for compliance with the Contract Work;

- Control of the process of verification of the minimum guaranteed parameters within the Performance and Guarantee Tests and confirmation that the Project meets the guaranteed parameters according to the Contract for Work, in particular:

  - Control of the Line parameters at different power levels of the boiler and turbine in different modes of electricity and heat production;

  - Control of full flow quantities and losses;

  - Check of turbine control characteristics, measurement of dynamic properties of the boiler/turbomachinery/CZT system, verification of performance and characteristics of coolers;

  - Control of the characteristics of the regenerative heating of condensate within the steam cycle and control of the characteristics of the thermal treatment of water and degassing;

  - Checking the parameters and separation characteristics of the flue gas cleaning system and the achieved emission quality parameters;

  - Control of output slag parameters, etc.

Test operation

The Construction Manager will supervise a trial run of at least 3 months, which will commence provided the following conditions are met:

- successful completion of tests - completion of installation, commissioning and testing, Performance tests, carried out prior to commencement of test operation;

- Handover of the Work;

- the effectiveness (legal force) of the decision of the building authority authorizing or ordering the test operation or the approval of the work;

- the consent of third parties, if such consent is required by law for the test operation

The test operation shall verify compliance with the parameters of the Work and the requirements under the Contract for the Work in accordance with the agreed test plan. The Contractor shall send the report to the Construction Manager without undue delay, but no later than 7 days after the completion of the test run.

For the supervision of the Construction Manager over the test operation, the permanent presence of the relevant members of the implementation team in the Client's operation is not required; the method of supervision will be subject to agreement between the Construction Manager and the Client.

Handover of the Work

The Handover process will commence upon the Contractor giving not less than 28 days' written notice that the Work is ready for handover. Within 14 days of receipt of the Handover Schedule, the Construction Manager shall provide the Contractor with his comments and instructions on the draft Schedule.

The Construction Manager shall commence the process of Handover of the Work upon the following conditions being met.

- the Work is in accordance with the requirements defined in the Work Contract;

- the Client has accepted the results of the tests required to be carried out in the Client's requirements prior to Handover of the Work;

- the documentation of the line will be submitted to the client in a form approved by the client;

- the construction site is properly and completely cleared, unless the parties agree otherwise;

- Staff	of the client	were	by the contractor	trained;

- a final itemised priced list of all work actually carried out will be submitted and agreed;

- the work is free from legal defects, in particular no third party claims any rights to the work or any part thereof

The Handover of the Work shall be effected by signing the Handover Protocol, which shall be drawn up by the Contractor in accordance with the requirements of the Construction Manager.

The construction manager is entitled to take over the work even with defects, provided that they do not substantially hinder the operation of the work or substantially restrict it and do not prevent the reliable and safe operation of the work.

Co-occupancy consent (decision)

The construction manager provides all necessary assistance to the contractor to issue the approval or other decision allowing the use of the line, with optimal continuity with the test operation so that the smooth operation of the line is not affected.

Warranty period

The warranty period follows the signing of the protocol of Handover of the Work by both parties, which lasts 24 months. The purpose of the warranty period is to verify that the Work, when in operation, will meet the requirements as defined in the Requirements The Construction Manager, in cooperation with the Contractor, shall draw up a report on the commencement of the warranty period. The Construction Manager shall be entitled to decide, at the Client's instruction, to extend the warranty period for a period of not more than 24 months from the expected end date of the warranty period if the Line does not achieve the guaranteed parameters during operation. The Client shall decide on this fact no later than 21 days before the date of the planned end of the guarantee period and at the same time notify the Contractor in writing. After the end of the first year of the warranty period, a test will be carried out to verify the parameters of the work. No later than 14 days after the expiry of the guarantee period, the contractor shall submit to the construction manager a report on the progress of the guarantee period. The client shall confirm this report by signing the guarantee period. The report shall indicate which tests have been carried out in accordance with the client's requirements and what the results were. The client shall confirm this report by his signature if the facts stated in the report correspond to the actual course of the guarantee period and the results of the tests to the testing carried out. The contractor shall submit to the client, together with the report according to the first sentence, the current form of the documents.

# List of tables

Table 1 - Qualitative and quantitative risk analysis of the project	9

Table 2 - Prevention of selected risks	11

Table 3 - Dates of documentation checks and reports to be submitted	23

# Attachments

Annex 	Contract documentation management scheme

Annex 2	Current documentation management scheme

Annex 3	Draft content and structures of reports

Contents of the interim report of the Construction Manager on the progress of the Work

The report will include:

- Home page including reference to the Contract, o Work of the Contractor's name and reporting period.

- Content of the report.

- The Construction Manager's comments on the individual parts of the monthly report(s) prepared by the Contractor (including attachments) in the period since the last interim report, for clarity in the structure of the Contractor's monthly report under the Contract for Work.

The statements, if they describe deficiencies on the part of the Contractor, will also include the Principal's recommendations for remedial action that has already been or should be required of the Contractor.

- Further comments by the Construction Manager on the Contractor's activities and the progress of the Construction Project in general, in particular:

  - Project economics and budget:

    - An opinion on the payments and future payment plan submitted by the Contractor in the course of the Work, in particular with regard to eligibility under the Work Contract.

    - Continuous control of the planned budget and real costs during project, i.e.:

      - in the preparation of the project documentation (extra work in the preparation of the project documentation and prediction of any resulting extra work in the implementation),

      - during the actual implementation.

    - Opinion on the Contractor's justifications and explanations regarding, related recommendations of the Construction Manager.

  - Results of the inspection of the construction log since the last interim report.

- More information about the activities of the Construction Manager:

  - Photographic documentation of the progress of the Work taken by the Principal (in the form of a link to a remote access repository).

  - The organisation/employees of the Principal:

- Changes in the organisation or employees of the Principal

- Final recommendations on the further progress of the Work.

- Attachments:

  - Updated organisational structure of the Principal (including position, name and contact details) - if changed

  - Updated list of change procedures (claims of the Client and the Contractor)

  - Updated list of correspondence and serious instructions of the Principal with the Contractor

  - Other attachments as required

Basic structure of the report on the commencement of the Principal's activities

- Evaluation of the completeness and relevance of the documentation received from the Principal.

- Basic opinion on the current Project Schedule.

- Updating the baseline apparent identified Project risks and their management.

- Recommendation to the Principal.

- Other attachments as necessary.

Basic structure of the Site Handover Report

- Assistance in the preparation of the site handover protocol.

The assistance in the preparation of the site handover report will mainly concern checking for accuracy and completeness:

  - description of the Site,

  - description of land ownership rights,

  - the description of the permission to enter the land,

  - a description of the special measures for carrying out the work,

  - list of permits and documents submitted,

  - plotting of basic height and direction points,

  - description of the Contractor's access regime to the Site,

  - description of utility connection points,

  - determination of areas for landfill of construction and assembly materials,

  - designation of a landfill site for waste, including a waste management regime,

  - determination of site facilities, i.e. administrative facilities of the Contractor and the Principal.

  - underground utility surveys,

- Photo and video documentation.

- Other attachments as necessary.

Basic structure of the Basic design report

- Basic assessment in terms of meeting the conditions specified by the Principal under the Contract for Work.

- Inspection of technical and capacity parameters within the scope of the Contract for Work (machinery, electrical equipment and automation).

- Basic assessment of the layout and process design in the scope of the Contract for Work (layout, building and construction part, process and balance diagrams).

- Assessment of the new facility in relation to the Existing Facility.

- Inspection of the Contractor's method of ensuring the functionality of the Existing Equipment during the Line Construction.

- Solution of transport routes and fulfillment of the conditions set at the handover of the Site.

- Compliance with technical, fire, environmental regulations including OSH.

- Compliance with Czech legislation and legal regulations.

- Compliance with the decisions of the Control Authorities issued so far.

- Evaluation of the original and proposed schedule of works.

- Evaluation of the total cost of implementation.

- Assessment of potential risks and their specific potential impacts on the Project.

- Recommendation to the Principal.

- Other attachments as necessary.

Basic structure of the final planning permission report

- Consideration of comments made during the construction procedure.

- Assessment of compliance with the conditions set out in the Permits issued to date.

- Statement on the conditions set by the Controlling Authorities for the execution of the works and impacts on the further implementation of the Project.

- Recommendation to the Principal.

- Other attachments as necessary.

Basic structure of the report on contractual milestones (according to Part II.h Contractual Schedule of the Contract for Work)

With respect to the relevant milestone, the Construction Manager, in prior consultation with the Client, shall propose a report structure for the milestone, taking into account whether any of the activities listed below are relevant to the milestone:

- Assessment of the status of the Project and Line Documentation in relation to the requirements under the Contract for Work for the milestone.

- Any additional opinion on the plan and subsequent output of the tests.

- Assessment of the condition of the construction part, mechanical and electrical installation of the equipment, including subsystems (alignment, grouting, alignment, testing of functional groups, final inspection, etc.) in the scope of the Contract for Work.

- An opinion on the completeness of the list of defects and deficiencies and its plan of elimination, including the potential impact on the further implementation of the Project.

- Compliance with the Legal Regulations under the Contract for the Work.

- Compliance with the decisions of the Control Authorities issued so far.

- Evaluation of the original and proposed schedule of works.

- Assessment of potential risks and their possible specific impacts on the Project.

- Assessment of the overall state of readiness of the Project for the downstream phase and recommendations to the Principal.

- Other attachments as necessary.